## Dashboard
IMTITHAL · PROJECT INITIATION & GOVERNANCE DASHBOARD
Project Management System · PMBOK® Guide – Eighth Edition Aligned · Reference IMT-PIG-XL-02 · Version 1.0 · Document Owner: PMO · Approval Authority: Portfolio Board · Effective 01-Sep-2026 · Status: Approved – Issued for Use
ACTIVE PROJECTS | TOTAL IN PORTFOLIO | AWAITING APPROVAL |  | AWAITING STAGE GATE
11 | 12 | 4 |  | 4
CRITICAL GOVERNANCE ISSUES | MISSING CHARTER | MISSING BUSINESS CASE |  | PORTFOLIO READINESS SCORE
3 | 4 | 3 |  | 70.8333
PROJECTS RATED READY | PROJECTS RAG RED | APPROVED BUDGET (PORTFOLIO) |  | FORECAST AT COMPLETION
7 | 2 | 26420000 |  | 27008000
PORTFOLIO ANALYSIS
EXCEPTION WATCH LIST
Exception |  | Count | Assessment
Projects with no approved Charter |  | 4 | ACTION REQUIRED
Projects with no approved Business Case |  | 3 | ACTION REQUIRED
Projects awaiting an approval decision |  | 4 | ACTION REQUIRED
Projects awaiting a stage gate decision |  | 4 | ACTION REQUIRED
Gate submissions overdue |  | 0 | CLEAR
Projects with critical or high governance issues |  | 3 | ACTION REQUIRED
Projects without initiation registers established |  | 5 | ACTION REQUIRED
Projects where the kick-off has not been held |  | 3 | ACTION REQUIRED
Projects rated Not Ready |  | 3 | ACTION REQUIRED
Projects forecast to exceed the approved budget |  | 5 | ACTION REQUIRED
Projects with a Red overall RAG status |  | 2 | ACTION REQUIRED
Projects on hold |  | 1 | ACTION REQUIRED
Data source: Portfolio_Master worksheet. Chart categories are maintained on the Calc worksheet — update the editable label lists for Project Manager and Business Unit to match your portfolio. Rows shaded gold in Portfolio_Master are example data; delete them before live use. PMI®, PMBOK® and PMP® are registered marks of the Project Management Institute, Inc. IMTITHAL is not affiliated with, endorsed by or approved by PMI.

## Portfolio_Master
IMTITHAL ¦ PROJECT MANAGEMENT SYSTEM ¦ PMBOK® GUIDE – EIGHTH EDITION ALIGNED
IMT-PIG-XL-02 · Portfolio Master — Project Initiation & Governance Data — The single data source for the dashboard. Enter one row per project.
Project: __________________ · Project Ref: __________ · Version: 1.0 · Document Owner: PMO · Approval Authority: Project Sponsor · Effective Date: 01-Sep-2026 · Revision Date: 01-Sep-2026 · Status: Approved – Issued for Use
Project ID | Project Name | Business Unit | Project Manager | Project Sponsor | Delivery Approach | Governance Tier | Project Phase | Project Status | Charter Status | Business Case Status | Overall Approval Status | Next Stage Gate | Gate Submission Due | Gate Decision Status | Governance Issue Level | Initiation Registers Established | Kick-off Held | Approved Budget | Spend to Date | Forecast at Completion | Planned Start | Planned Finish | Readiness Score | Readiness Band | Overall RAG | Last Updated
PRJ-2026-001 | Customer Onboarding Automation | Retail Operations | S. Haddad | M. Al-Rashid | Hybrid | Tier 1 | Execution | In Progress | Approved | Approved | Approved | G3 - Delivery Readiness | 2026-09-18 | Scheduled | Low | Yes | Yes | 2400000 | 1180000 | 2510000 | 2026-02-02 | 2027-04-30 | 97 | Ready | Amber | 2026-08-10
PRJ-2026-002 | Core Banking Interface Upgrade | Technology | R. Nasser | L. Farouk | Predictive | Tier 1 | Planning | In Progress | Approved | Approved | Approved | G2 - Planning | 2026-08-28 | Awaiting decision | Medium | Yes | Yes | 5600000 | 860000 | 5750000 | 2026-05-11 | 2027-11-30 | 92 | Ready | Amber | 2026-08-11
PRJ-2026-003 | Regulatory Reporting Compliance | Risk & Compliance | H. Idris | N. Suleiman | Predictive | Tier 1 | Execution | In Progress | Approved | Approved | Approved | G4 - Deployment Readiness | 2026-10-06 | Scheduled | Critical | Yes | Yes | 3100000 | 2240000 | 3480000 | 2026-01-12 | 2026-12-31 | 85 | Ready | Red | 2026-08-12
PRJ-2026-004 | Field Service Mobile Application | Field Operations | K. Mansour | D. Othman | Agile | Tier 2 | Execution | In Progress | Approved | Approved | Approved | G4 - Deployment Readiness | 2026-09-04 | Scheduled | None | Yes | Yes | 980000 | 610000 | 965000 | 2026-03-02 | 2027-01-29 | 100 | Ready | Green | 2026-08-12
PRJ-2026-005 | Warehouse Layout Optimisation | Supply Chain | A. Zahra | T. Bakr | Predictive | Tier 2 | Initiation | In Progress | Under Review | Approved | Pending | G1 - Initiation | 2026-08-25 | Awaiting decision | Medium | No | Yes | 1450000 | 42000 | 1450000 | 2026-09-01 | 2027-06-30 | 54 | Gaps | Amber | 2026-08-11
PRJ-2026-006 | HR Self-Service Portal | Human Resources | S. Haddad | F. Qasim | Hybrid | Tier 2 | Planning | In Progress | Approved | Approved | Approved | G2 - Planning | 2026-09-11 | Scheduled | Low | Yes | Yes | 720000 | 95000 | 735000 | 2026-06-15 | 2027-03-31 | 97 | Ready | Green | 2026-08-10
PRJ-2026-007 | Data Platform Consolidation | Technology | R. Nasser | L. Farouk | Hybrid | Tier 1 | Initiation | In Progress | In Progress | Approved | Pending | G1 - Initiation | 2026-09-29 | Awaiting decision | High | No | No | 4200000 | 0 | 4200000 | 2026-10-01 | 2028-03-31 | 29 | Not Ready | Amber | 2026-08-12
PRJ-2026-008 | Branch Network Refurbishment | Retail Operations | M. Sabri | M. Al-Rashid | Predictive | Tier 2 | Execution | In Progress | Approved | Approved | Approved | G4 - Deployment Readiness | 2026-11-02 | Not due | None | Yes | Yes | 6800000 | 3950000 | 6740000 | 2025-11-03 | 2027-08-31 | 100 | Ready | Green | 2026-08-09
PRJ-2026-009 | Procurement Process Redesign | Finance | A. Zahra | T. Bakr | Agile | Tier 3 | Planning | On Hold | Approved | Under Review | Pending | G2 - Planning | 2026-08-20 | Hold pending actions | High | No | Yes | 310000 | 58000 | 340000 | 2026-04-06 | 2026-12-18 | 50 | Gaps | Red | 2026-08-08
PRJ-2026-010 | Sustainability Reporting Framework | Risk & Compliance | H. Idris | N. Suleiman | Hybrid | Tier 3 | Initiation | In Progress | Not Started | Under Review | Pending | G1 - Initiation | 2026-09-15 | Awaiting decision | Medium | No | No | 260000 | 0 | 260000 | 2026-10-12 | 2027-05-28 | 19 | Not Ready | Amber | 2026-08-12
PRJ-2026-011 | Contact Centre Workforce Tool | Customer Service | K. Mansour | D. Othman | Agile | Tier 3 | Closure | Completed | Approved | Approved | Approved | G5 - Closure | 2026-07-24 | Proceed | None | Yes | Yes | 420000 | 398000 | 398000 | 2025-09-01 | 2026-07-31 | 100 | Ready | Green | 2026-08-01
PRJ-2026-012 | Legacy Archive Decommissioning | Technology | M. Sabri | L. Farouk | Predictive | Tier 3 | Concept | Not Started | Not Started | Not Started | Not Required | G0 - Concept | 2026-10-20 | Not due | Low | No | No | 180000 | 0 | 180000 | 2027-01-04 | 2027-09-30 | 27 | Not Ready | Green | 2026-08-12

## Calc
IMTITHAL ¦ PROJECT MANAGEMENT SYSTEM ¦ PMBOK® GUIDE – EIGHTH EDITION ALIGNED
IMT-PIG-XL-03 · Dashboard Calculation Tables — Formula driven — do not edit except the label columns marked as editable
Project: __________________ · Project Ref: __________ · Version: 1.0 · Document Owner: PMO · Approval Authority: Project Sponsor · Effective Date: 01-Sep-2026 · Revision Date: 01-Sep-2026 · Status: Approved – Issued for Use
| PROJECTS BY STATUS |  | PROJECTS BY PROJECT MANAGER |  | PROJECT APPROVAL STATUS
| Category | Projects | Category (editable) | Projects | Category | Projects
| Not Started | 1 | S. Haddad | 2 | Approved | 7
| In Progress | 9 | R. Nasser | 2 | Approved with conditions | 0
| Under Review | 0 | H. Idris | 2 | Pending | 4
| Approved | 0 | K. Mansour | 2 | Rejected | 0
| On Hold | 1 | A. Zahra | 2 | Not Required | 1
| Completed | 1 | M. Sabri | 2
| Cancelled | 0 |  | 0 | GOVERNANCE ISSUE LEVEL
| Rejected | 0 |  | 0 | Category | Projects
|  |  | Maintain this label list to match the project managers in the portfolio. |  | None | 3
| PROJECTS BY DELIVERY APPROACH |  |  |  | Low | 3
| Category | Projects |  |  | Medium | 3
| Predictive | 5 |  |  | High | 2
| Agile | 3 | PROJECTS BY BUSINESS UNIT |  | Critical | 1
| Hybrid | 4 | Category (editable) | Projects
|  |  | Retail Operations | 2 | GATE DECISION STATUS
| PROJECTS BY GOVERNANCE TIER |  | Technology | 3 | Category | Projects
| Category | Projects | Risk & Compliance | 2 | Awaiting decision | 4
| Tier 1 | 4 | Field Operations | 1 | Scheduled | 4
| Tier 2 | 4 | Supply Chain | 1 | Proceed | 1
| Tier 3 | 4 | Human Resources | 1 | Proceed with conditions | 0
| Fast-track | 0 | Finance | 1 | Hold pending actions | 1
|  |  | Customer Service | 1 | Re-plan and resubmit | 0
| PROJECT READINESS BAND |  |  | 0 | Terminate | 0
| Category | Projects |  | 0 | Not due | 2
| Ready | 7 | Maintain this label list to match the business units in the portfolio.
| Nearly Ready | 0
| Gaps | 2
| Not Ready | 3

## Lists
IMTITHAL ¦ CONTROLLED VALUE LISTS — do not rename this sheet or the defined names
Status | Approach | Tier | Phase | DocStatus | ApprovalStatus | Gate | GateDecision | IssueLevel | YesNo | RAG | Band
Not Started | Predictive | Tier 1 | Concept | Not Started | Approved | G0 - Concept | Awaiting decision | None | Yes | Green | Ready
In Progress | Agile | Tier 2 | Initiation | In Progress | Approved with conditions | G1 - Initiation | Scheduled | Low | No | Amber | Nearly Ready
Under Review | Hybrid | Tier 3 | Planning | Under Review | Pending | G2 - Planning | Proceed | Medium | N/A | Red | Gaps
Approved |  | Fast-track | Execution | Approved | Rejected | G3 - Delivery Readiness | Proceed with conditions | High |  |  | Not Ready
Rejected |  |  | Deployment | Rejected | Not Required | G4 - Deployment Readiness | Hold pending actions | Critical
On Hold |  |  | Closure | Not Required |  | G5 - Closure | Re-plan and resubmit
Completed |  |  | Closed |  |  | None | Terminate
Cancelled | [6 empty] | Not due