IMTITHAL PROJECT MANAGEMENT SYSTEM PMBOK® Guide – Eighth Edition Aligned

TOOLKIT 01  |  PROJECT INITIATION & GOVERNANCE

TOOLKIT IMPLEMENTATION GUIDE

How to deploy and operate the Project Initiation & Governance Toolkit

Document Reference:  IMT-PIG-UG-01

| DOCUMENT CONTROL |  |  |  |
| --- | --- | --- | --- |
| File Name | IMT-PIG-UG-01_Toolkit_Implementation_Guide_v1.0.docx | Version | 1.0 |
| Document Owner | Project Management Office (PMO) | Document Status | Approved – Issued for Use |
| Approval Authority | Head of PMO / Portfolio Director | Classification | Internal – Controlled Document |
| Effective Date | 01-Sep-2026 | Revision Date | 01-Sep-2026 |
| Next Review Date | 01-Sep-2027 | Review Frequency | Annually, and following any material change to the organisational methodology or governance framework |

IMTITHAL Project Management System · Toolkit 01: Project Initiation & Governance This document is an original IMTITHAL work product developed in alignment with the concepts and practices of the PMBOK® Guide – Eighth Edition. PMI, PMBOK, PMP and PMI-ACP are marks of the Project Management Institute, Inc. IMTITHAL is not affiliated with, endorsed by, certified by, or approved by PMI. No PMI copyrighted text or proprietary PMI template is reproduced herein.

# 1.  Purpose

This guide explains how to deploy the IMTITHAL Project Initiation & Governance Toolkit within an organisation and how to operate it on an individual project. It describes the toolkit architecture, the sequence in which the documents are used, the responsibilities of each role, the tailoring rules applied by governance tier, the deployment approach for a PMO introducing the toolkit for the first time, and the measures by which adoption and effectiveness are monitored.

- Provides the deployment route for a PMO introducing the toolkit organisation-wide.

- Gives project managers the operating sequence for a single project.

- Explains how the Word templates, Excel registers and dashboard interlock.

- Defines the tailoring rules applied at each governance tier.

# 2.  When to Use

- When an organisation adopts the toolkit for the first time.

- When onboarding a project manager, PMO analyst or sponsor to the toolkit.

- At the start of every project, to confirm the applicable document set and sequence.

- When reviewing the effectiveness of the toolkit and planning improvements.

# 3.  Responsibility and Approval

| Governance Role | Assignment | Description of Involvement |
| --- | --- | --- |
| Responsible (prepares) | PMO Manager | Prepares, populates and maintains the document; ensures accuracy and completeness of all fields. |
| Accountable (owns) | Head of PMO / Portfolio Director | Single point of accountability for the quality, currency and control of the document. |
| Consulted | PMO, Finance, Risk, Quality, Legal/Contracts, business owners and technical disciplines as applicable | Provides subject-matter input before submission for approval. |
| Informed | Project team, affected business units, supporting functions, key external stakeholders | Receives the approved document through the controlled distribution list. |
| Approves | Head of PMO / Portfolio Director | Formally authorises the document; approval is recorded in the Project Approval Register. |

# 4.  Required Inputs

- Organisational project management methodology and governance framework.

- Current project portfolio and its distribution by value, complexity and risk.

- Existing templates and registers in use, for mapping and migration.

- Delivery capability and maturity assessment.

- Organisational delegation of authority policy and records retention policy.

# 5.  Required Outputs

- A deployed and configured toolkit with organisational parameters set.

- A trained population of project managers, sponsors and PMO staff.

- A defined document set and tailoring rule applied per governance tier.

- Adoption and compliance measures reported through the PMO.

# 6.  PMBOK® Guide – Eighth Edition Alignment

This document has been designed in alignment with the following elements of the PMBOK® Guide – Eighth Edition. The alignment statement is provided for conceptual traceability only.

| Focus Area | Applies across all focus areas; primarily supports Initiating and Planning |
| --- | --- |
| Performance Domains | Governance (primary); all performance domains supported by the toolkit content |
| Guiding Principles | Adopt a holistic view · Focus on value · Embed quality into processes and deliverables · Be an accountable leader · Build an empowered culture · Integrate sustainability |
| Tailoring Consideration | The toolkit is designed to be tailored. Section E of this guide defines the minimum mandatory document set by governance tier; anything beyond the minimum is applied where it adds control value. |

# 7.  Review Frequency and Approval Requirements

| Review Frequency | Annually, and following any material change to the organisational methodology or governance framework |
| --- | --- |
| Review Triggers | Change of sponsor or governance structure; change of delivery approach; stage-gate decision; material change to scope, cost, schedule, benefits or risk exposure; audit or assurance finding; organisational restructuring. |
| Approval Requirements | Formal written approval by the stated Approval Authority before the document is baselined and distributed. Approval is logged in the Project Approval Register (IMT-PIG-021). |
| Change Control | Any change to an approved version requires a change request assessed through the project change control process. Minor editorial changes increment the minor version; changes affecting scope, cost, schedule, benefits or governance increment the major version and require re-approval. |
| Retention | Retained for the life of the project plus the organisational records-retention period, in the Project Information and Document Register. |

# 8.  Instructions for Completion

Complete every field. Where a field is not applicable, enter "N/A" and state the reason — never leave a field blank.

- Read Section B to understand the toolkit architecture and how the three components interlock.

- Configure the organisational parameters listed in Section C before the toolkit is issued for use — thresholds, tiers, gate model and controlled value lists.

- Follow the deployment sequence in Section D. Deploy on a pilot project before organisation-wide release.

- Apply the tier-based document set in Section E. Do not require Tier 3 projects to complete the full Tier 1 set — disproportionate control is the fastest route to non-compliance.

- Use the project operating sequence in Section F on every project. The sequence is deliberately ordered so that each document has the inputs it needs when it is produced.

- Use the role guidance in Section G when briefing sponsors, project managers, PMO staff and business owners.

- Configure the Excel registers and dashboard as described in Section H before first use.

- Monitor adoption using the measures in Section I and report them through the PMO governance route.

- Manage toolkit changes through Section J. Amendments are versioned centrally; project teams must not maintain local variants.

NOTE The most common cause of toolkit failure is issuing the templates without configuring the organisational parameters in Section C. An unconfigured threshold or an unnamed governance body converts a control into a blank field.

# 9.  Implementation Guide

## Section A — Toolkit Contents

Toolkit 01 — Project Initiation & Governance comprises twenty-six controlled documents, one master Excel register workbook, one portfolio dashboard, three user guides and a master index.

| Component | Contents | Location | Instance |
| --- | --- | --- | --- |
| Word Templates | 26 controlled documents and forms, each with purpose, usage, responsibility, inputs, outputs, instructions, review frequency, approval requirements and revision history | Word_Templates | One completed copy per project |
| Excel Registers | Master workbook containing the project profile, eight controlled registers, the scored approach assessment, the RACI matrix and an automatic register summary | Excel_Registers | One workbook per project |
| Dashboard | Portfolio-level initiation and governance dashboard with twelve KPI cards, nine charts and an exception watch list | Dashboards | One workbook per portfolio |
| User Guides | Implementation guide, register user guide and dashboard user guide | User_Guides | Organisational reference |
| Master Index | Controlled index of every file with version, owner, approval authority, effective date, revision date and status | Master_Index | Organisational reference |

## Section B — Toolkit Architecture

The three working components are designed to interlock. The Word template defines the control — its purpose, rules, approval requirements and instructions. The Excel register is the live working instance of that control for a specific project. The dashboard aggregates the resulting data across the portfolio.

| Control | Word Template | Excel Worksheet | Dashboard Contribution |
| --- | --- | --- | --- |
| Benefits identification | IMT-PIG-006 | Benefits_Register | Portfolio benefit total |
| Benefits realisation | IMT-PIG-007 | Benefits_Realisation | Realisation RAG |
| Responsibility assignment | IMT-PIG-013 | RACI_Matrix | Accountability defect count |
| Approach suitability | IMT-PIG-016 | Approach_Assessment | Projects by delivery approach |
| Assumptions | IMT-PIG-018 | Assumptions_Log | Governance issue level |
| Constraints | IMT-PIG-019 | Constraints_Log | Governance issue level |
| Dependencies | IMT-PIG-020 | Dependencies_Register | Governance issue level |
| Approvals | IMT-PIG-021 | Approval_Register | Projects awaiting approval |
| Stage gates | IMT-PIG-022 | Stage_Gate_Tracker | Projects awaiting stage gate |
| Actions | IMT-PIG-024 | Action_Log | Exception watch list |
| Document control | IMT-PIG-026 | Document_Register | Missing charter / business case |

## Section C — Organisational Parameters to Configure Before First Use

Complete the parameters below before the toolkit is issued. Each parameter appears as a placeholder in one or more templates.

| Ref | Parameter | Where It Is Used | Organisational Value | Set By | Date Set |
| --- | --- | --- | --- | --- | --- |

| Ref | Parameter | Where It Is Used | Organisational Value | Set By |
| --- | --- | --- | --- | --- |
| C1 | Major project value threshold (Tier 1) | IMT-PIG-008 §B |  | Portfolio Board |
| C2 | Minor project value threshold (Tier 3) | IMT-PIG-008 §B |  | Portfolio Board |
| C3 | Project manager expenditure limit | IMT-PIG-011 §C |  | Finance |
| C4 | Sponsor expenditure limit | IMT-PIG-011 §C |  | Finance |
| C5 | Cost tolerance before re-approval | IMT-PIG-002 §J |  | Investment Board |
| C6 | Schedule tolerance before escalation | IMT-PIG-002 §J |  | Investment Board |
| C7 | Benefit tolerance before re-approval | IMT-PIG-002 §J |  | Investment Board |
| C8 | Discount rate and appraisal period | IMT-PIG-002 §F |  | Finance |
| C9 | Gate model applied per tier | IMT-PIG-008 §D |  | Head of PMO |
| C10 | Governance bodies and their chairs | IMT-PIG-008 §C |  | Executive Management |
| C11 | Escalation response times | IMT-PIG-008 §F |  | Head of PMO |
| C12 | Mandatory controls that may not be tailored out | IMT-PIG-017 §C |  | Head of PMO |
| C13 | Records retention periods by category | IMT-PIG-026 §F |  | Records / Legal |
| C14 | Information classification levels | IMT-PIG-026 §B |  | Information Security |
| C15 | Business unit and project manager label lists | Dashboard Calc worksheet |  | PMO |
| C16 | Currency and price base | IMT-PIG-002 §A |  | Finance |

## Section D — Deployment Sequence

| Step | Activity | Description | Owner | Typical Duration |
| --- | --- | --- | --- | --- |
| 1 | Assess and map | Compare the toolkit against existing templates; identify what is replaced, merged or retired | PMO Manager | 1–2 weeks |
| 2 | Configure parameters | Complete every parameter in Section C and obtain approval from the owning function | PMO Manager | 2–3 weeks |
| 3 | Approve the framework | Obtain executive approval of IMT-PIG-008 as the organisational governance framework | Head of PMO | 2–4 weeks |
| 4 | Configure the workbooks | Set controlled value lists, thresholds and label lists in the Excel registers and dashboard | PMO Analyst | 1 week |
| 5 | Pilot | Apply the full toolkit to one Tier 2 project from initiation to the planning gate | Pilot Project Manager | 6–10 weeks |
| 6 | Review and adjust | Capture pilot lessons; amend templates and parameters; re-issue at version 1.1 | PMO Manager | 2 weeks |
| 7 | Train | Brief project managers, sponsors, business owners and PMO staff; issue the user guides | PMO Manager | 2–4 weeks |
| 8 | Release | Publish the approved toolkit with an effective date and a transition rule for projects already in flight | Head of PMO | 1 week |
| 9 | Monitor | Track adoption and compliance using the measures in Section I; report through PMO governance | PMO Manager | Continuous |
| 10 | Improve | Review annually; amend through the change route in Section J | PMO Manager | Annual |

NOTE Transition rule for projects already in delivery: apply the toolkit from the next stage gate rather than retrospectively. Requiring in-flight projects to produce initiation artefacts retrospectively produces documentation without control value.

## Section E — Minimum Document Set by Governance Tier

| Reference | Document | Tier 1 | Tier 2 | Tier 3 |
| --- | --- | --- | --- | --- |
| IMT-PIG-001 | Project Charter | Mandatory | Mandatory | Mandatory |
| IMT-PIG-002 | Business Case | Mandatory (full) | Mandatory (full) | Mandatory (short form) |
| IMT-PIG-003 | Project Proposal | Mandatory | Mandatory | Mandatory |
| IMT-PIG-004 | Initiation Checklist | Mandatory | Mandatory | Mandatory (reduced) |
| IMT-PIG-005 | Objectives and Success Criteria | Mandatory | Mandatory | Mandatory |
| IMT-PIG-006 | Benefits Identification Register | Mandatory | Mandatory | Mandatory |
| IMT-PIG-007 | Benefits Realisation Plan | Mandatory | Mandatory | Merged into IMT-PIG-006 |
| IMT-PIG-008 | Governance Framework | Organisational | Organisational | Organisational |
| IMT-PIG-009 | Governance Structure | Mandatory | Mandatory | Reduced |
| IMT-PIG-010 | Decision-Making Matrix | Mandatory | Mandatory | Optional |
| IMT-PIG-011 | Authority Matrix | Mandatory | Mandatory | Mandatory |
| IMT-PIG-012 | Roles and Responsibilities Matrix | Mandatory | Reduced | Optional |
| IMT-PIG-013 | RACI Matrix | Mandatory | Mandatory | Reduced |
| IMT-PIG-014 | Organisation Chart | Mandatory | Mandatory | Optional |
| IMT-PIG-015 | Approach Selection Form | Mandatory | Mandatory | Reduced |
| IMT-PIG-016 | Approach Suitability Assessment | Mandatory | Mandatory | Optional |
| IMT-PIG-017 | Tailoring Assessment | Mandatory | Mandatory | Mandatory |
| IMT-PIG-018 | Assumptions Log | Mandatory | Mandatory | Mandatory |
| IMT-PIG-019 | Constraints Log | Mandatory | Mandatory | Mandatory |
| IMT-PIG-020 | Dependencies Register | Mandatory | Mandatory | Mandatory |
| IMT-PIG-021 | Approval Register | Mandatory | Mandatory | Mandatory |
| IMT-PIG-022 | Stage / Gate Approval Form | Mandatory (all gates) | Mandatory (G1, G3, G5) | Mandatory (G1, G5) |
| IMT-PIG-023 | Kick-Off Meeting Agenda | Mandatory | Mandatory | Mandatory (compressed) |
| IMT-PIG-024 | Kick-Off Meeting Minutes | Mandatory | Mandatory | Mandatory |
| IMT-PIG-025 | Project Management Plan Index | Mandatory | Mandatory | Reduced |
| IMT-PIG-026 | Information and Document Register | Mandatory | Mandatory | Mandatory (reduced) |

## Section F — Project Operating Sequence

| Step | Stage | Activity and Document | Produced By | Approved By |
| --- | --- | --- | --- | --- |
| 1 | Demand | Submit the Project Proposal (003) for screening | Requesting manager | Portfolio Board |
| 2 | Justify | Develop the Business Case (002) with the benefits register (006) | Business owner | Investment Board |
| 3 | Define | Complete Objectives and Success Criteria (005) | Project manager | Sponsor |
| 4 | Authorise | Draft and approve the Project Charter (001) | Project manager | Sponsor |
| 5 | Govern | Apply the Framework (008); define the Structure (009), Decision Matrix (010) and Authority Matrix (011) | Project manager | Sponsor |
| 6 | Organise | Complete Roles and Responsibilities (012), RACI (013) and the Organisation Chart (014) | Project manager | Sponsor |
| 7 | Choose | Run the Suitability Assessment (016); complete Approach Selection (015) | Project manager and team | Sponsor and PMO |
| 8 | Tailor | Complete the Tailoring Assessment (017) | Project manager | PMO and Sponsor |
| 9 | Surface | Establish the Assumptions (018), Constraints (019) and Dependencies (020) registers | Project manager | Sponsor |
| 10 | Control | Establish the Approval Register (021) and Document Register (026) | Project manager | PMO |
| 11 | Mobilise | Hold the kick-off using the Agenda (023); issue the Minutes (024) | Project manager | Sponsor |
| 12 | Assure | Complete the Initiation Checklist (004); verify with the PMO | Project manager | PMO and Sponsor |
| 13 | Gate | Submit the Stage / Gate Approval Form (022) for Gate 1 | Project manager | Gate authority |
| 14 | Plan | Assemble the plan using the Plan Index (025) | Project manager | Sponsor |
| 15 | Realise | Operate the Benefits Realisation Plan (007) through to handover | Business owner | Sponsor |

## Section G — Role Guidance

| Role | What the Toolkit Requires of You | Documents You Own or Approve |
| --- | --- | --- |
| Project Sponsor | Approve the charter and the objectives; set authority thresholds; chair governance; take gate decisions; accept residual risk from tailoring | Approves 001, 005, 009, 010, 011, 017, 022 |
| Business Owner | Own the business case and the benefits; provide baselines; commit to the business change required for realisation | Owns 002, 006, 007 |
| Project Manager | Produce and maintain the initiation artefacts and registers; run the kick-off; submit gate packs; keep the registers current | Owns 001, 004, 009–015, 018–026 |
| PMO | Configure and maintain the toolkit; verify the initiation checklist; endorse tailoring; verify the approval register; report portfolio KPIs | Owns 008, UG-01 to UG-03; verifies 004, 017, 021 |
| Benefit Owner | Accept named accountability for a benefit; supply the measure; report realisation after handover | Endorses 006, 007 |
| Finance | Validate quantified benefits and cost estimates; confirm financial authority limits | Validates 002, 006, 011 |
| Delivery Team | Contribute to the suitability assessment, RACI and risk identification; work to the agreed ways of working | Contributes to 013, 016, 023, 024 |

## Section H — Configuring the Excel Components

- Open the master register workbook and complete the Project_Profile worksheet before any register is used. The profile carries the project identity used across every register.

- Review the Lists worksheet. Add organisational values inside the existing ranges so that the defined names expand automatically; never rename the defined names.

- Delete the example rows shaded in gold from every register before live use. They are provided to demonstrate the expected data format.

- Confirm that the Register_Summary worksheet computes. It is protected because every cell is a formula; if a value does not appear, check that data has been entered from row 6 downward.

- For the dashboard, complete the Portfolio_Master worksheet with one row per project and delete the example rows.

- Update the editable label lists on the dashboard Calc worksheet so that the project manager and business unit charts reflect your portfolio.

- Do not insert or delete columns in any register — the summary formulas, conditional formatting and dashboard aggregation reference fixed columns.

- Extend a register beyond sixty rows by selecting the last data row and using the table extend handle, so that formatting, validation and formulas carry down.

## Section I — Adoption and Effectiveness Measures

| Measure | Target | Frequency | Source |
| --- | --- | --- | --- |
| Projects with an approved charter before delivery starts | 100% | Monthly | Dashboard KPI |
| Projects with an approved business case before funding release | 100% | Monthly | Dashboard KPI |
| Initiation checklist completed and PMO verified before Gate 1 | 100% | Per gate | Checklist (004) |
| Average initiation readiness score at Gate 1 | ≥ 90 | Per gate | Dashboard KPI |
| Gate decisions taken within the defined response time | ≥ 90% | Quarterly | Stage gate tracker |
| Approvals granted outside the authority matrix | 0 | Quarterly | Approval register §E |
| Assumptions validated by their due date | ≥ 85% | Monthly | Assumptions log |
| Dependencies bilaterally confirmed before baseline | 100% | Per gate | Dependencies register |
| Tailoring assessments approved by the PMO | 100% | Per project | Tailoring assessment |
| Benefits with a named owner and a measured baseline | 100% | Per gate | Benefits register |

## Section J — Toolkit Change Control

| J1. Toolkit Owner | ⟨ PMO Manager ⟩ |
| --- | --- |
| J2. Change Request Route | ⟨ raised to the PMO; assessed for impact across all components ⟩ |
| J3. Approval Authority for Amendments | ⟨ Head of PMO; Executive Management for governance framework changes ⟩ |
| J4. Version Numbering | ⟨ minor version for editorial change; major version for a change of control ⟩ |
| J5. Release Cycle | ⟨ consolidated release annually; urgent corrections issued as needed ⟩ |
| J6. Communication of Changes | ⟨ change note issued with each release; version history maintained in the master index ⟩ |
| J7. Local Variants | ⟨ not permitted; tailoring is applied through IMT-PIG-017, not by amending templates ⟩ |

# 10.  Approval and Authorisation

By signing below, each approver confirms that the content of this document has been reviewed, is accurate to the best of their knowledge, and is authorised for use within the project.

| Approval Role | Name | Position / Title | Signature | Date |
| --- | --- | --- | --- | --- |
| Prepared by (PMO Manager) |  |  |  |  |
| Reviewed by (Internal Audit / Risk) |  |  |  |  |
| Approved by (Head of PMO) |  |  |  |  |

# 11.  Revision History

| Version | Date | Description of Change | Prepared / Revised By | Approved By |
| --- | --- | --- | --- | --- |
| 0.1 | DD-MMM-YYYY | Initial draft prepared for review | Project Manager | — |
| 0.9 | DD-MMM-YYYY | Reviewed by PMO; comments incorporated | PMO Analyst | — |
| 1.0 | 01-Sep-2026 | First approved and issued baseline | Project Manager | Head of PMO / Portfolio Director |

NOTE Rows shown in shaded italics are illustrative examples of how the revision history is completed. Replace them with the actual revision record.

# 12.  Notice and Disclaimer

PMI®, PMBOK®, PMP®, PMI-ACP® and PfMP® are registered marks of the Project Management Institute, Inc. This document is an original work product of IMTITHAL, developed in alignment with the principles, performance domains and focus areas described in the PMBOK® Guide – Eighth Edition. It is not issued, certified, endorsed or approved by PMI, and it does not reproduce PMI copyrighted text or proprietary PMI templates. Organisations remain responsible for tailoring this document to their own governance, contractual and regulatory obligations.