IMTITHAL PROJECT MANAGEMENT SYSTEM PMBOK® Guide – Eighth Edition Aligned

TOOLKIT 01  |  PROJECT INITIATION & GOVERNANCE

INITIATION AND GOVERNANCE DASHBOARD USER GUIDE

Operating and interpreting the portfolio dashboard

Document Reference:  IMT-PIG-UG-03

| DOCUMENT CONTROL |  |  |  |
| --- | --- | --- | --- |
| File Name | IMT-PIG-UG-03_Initiation_and_Governance_Dashboard_User_Guide_v1.0.docx | Version | 1.0 |
| Document Owner | Project Management Office (PMO) | Document Status | Approved – Issued for Use |
| Approval Authority | PMO Manager | Classification | Internal – Controlled Document |
| Effective Date | 01-Sep-2026 | Revision Date | 01-Sep-2026 |
| Next Review Date | 01-Sep-2027 | Review Frequency | Data refreshed monthly, or fortnightly for a portfolio with Tier 1 projects in flight |

IMTITHAL Project Management System · Toolkit 01: Project Initiation & Governance This document is an original IMTITHAL work product developed in alignment with the concepts and practices of the PMBOK® Guide – Eighth Edition. PMI, PMBOK, PMP and PMI-ACP are marks of the Project Management Institute, Inc. IMTITHAL is not affiliated with, endorsed by, certified by, or approved by PMI. No PMI copyrighted text or proprietary PMI template is reproduced herein.

# 1.  Purpose

This guide explains how to populate, operate and interpret the IMTITHAL Project Initiation & Governance Dashboard. It describes the Portfolio Master data structure, the definition and calculation of each KPI, the readiness scoring model, the charts and the exception watch list, the reporting cycle in which the dashboard is used, and the actions expected when an exception is raised.

- Explains what each KPI measures and exactly how it is calculated.

- Documents the readiness scoring model so that scores can be challenged and understood.

- Defines the data maintenance cycle that keeps the dashboard trustworthy.

- Sets out the expected governance response to each exception.

# 2.  When to Use

- When populating the dashboard for the first time.

- Before each portfolio governance meeting, when preparing the reporting pack.

- When a KPI or an exception requires interpretation or challenge.

- When adding a project to, or removing a project from, the portfolio.

# 3.  Responsibility and Approval

| Governance Role | Assignment | Description of Involvement |
| --- | --- | --- |
| Responsible (prepares) | PMO Analyst | Prepares, populates and maintains the document; ensures accuracy and completeness of all fields. |
| Accountable (owns) | PMO Manager | Single point of accountability for the quality, currency and control of the document. |
| Consulted | PMO, Finance, Risk, Quality, Legal/Contracts, business owners and technical disciplines as applicable | Provides subject-matter input before submission for approval. |
| Informed | Project team, affected business units, supporting functions, key external stakeholders | Receives the approved document through the controlled distribution list. |
| Approves | PMO Manager | Formally authorises the document; approval is recorded in the Project Approval Register. |

# 4.  Required Inputs

- Project data from each project's registers workbook and governance records.

- Charter, business case and approval status for every project in the portfolio.

- Stage gate schedule and decision status.

- Governance issue and RAG assessments from project reporting.

# 5.  Required Outputs

- A current portfolio dashboard with twelve KPI cards, nine charts and an exception watch list.

- An exception list driving portfolio governance discussion and action.

- Portfolio reporting input for the Portfolio Board pack.

# 6.  PMBOK® Guide – Eighth Edition Alignment

This document has been designed in alignment with the following elements of the PMBOK® Guide – Eighth Edition. The alignment statement is provided for conceptual traceability only.

| Focus Area | Monitoring and Controlling, applied at portfolio level |
| --- | --- |
| Performance Domains | Governance (primary); Finance, Stakeholders, Risk (supporting) |
| Guiding Principles | Focus on value · Adopt a holistic view · Be an accountable leader |
| Tailoring Consideration | Additional KPI cards or charts may be added; if so, extend the Calc worksheet aggregation tables rather than referencing Portfolio_Master directly from the Dashboard, so that the separation between data, calculation and presentation is preserved. |

# 7.  Review Frequency and Approval Requirements

| Review Frequency | Data refreshed monthly, or fortnightly for a portfolio with Tier 1 projects in flight |
| --- | --- |
| Review Triggers | Change of sponsor or governance structure; change of delivery approach; stage-gate decision; material change to scope, cost, schedule, benefits or risk exposure; audit or assurance finding; organisational restructuring. |
| Approval Requirements | Formal written approval by the stated Approval Authority before the document is baselined and distributed. Approval is logged in the Project Approval Register (IMT-PIG-021). |
| Change Control | Any change to an approved version requires a change request assessed through the project change control process. Minor editorial changes increment the minor version; changes affecting scope, cost, schedule, benefits or governance increment the major version and require re-approval. |
| Retention | Retained for the life of the project plus the organisational records-retention period, in the Project Information and Document Register. |

# 8.  Instructions for Completion

Complete every field. Where a field is not applicable, enter "N/A" and state the reason — never leave a field blank.

- Populate the Portfolio_Master worksheet with one row per project. Delete the gold-shaded example rows before live use.

- Complete every controlled column using the dropdowns. Blank controlled cells are excluded from the counts and will understate the exceptions.

- Leave the Readiness Score and Readiness Band columns alone. They are calculated and protected.

- Update the editable label lists on the Calc worksheet so that the project manager and business unit charts reflect your actual portfolio.

- Refresh the data on a fixed cycle before each portfolio governance meeting, and record the refresh date in the Last Updated column for each project.

- Read the KPI cards first, then the exception watch list. The exception list is the agenda for the portfolio meeting.

- Treat every red exception as requiring a named owner and a due date. A recurring exception with no owner indicates the dashboard is being read but not acted on.

- Challenge any project whose readiness score is high while its RAG status is red — the two should rarely diverge, and divergence usually indicates stale data.

- Do not edit the Dashboard or Calc worksheets directly; both are protected because every cell is a formula.

- Archive a dated copy after each portfolio meeting so that the trend across periods can be reconstructed.

NOTE A dashboard is only as honest as the data behind it. Where a project manager reports a status inconsistent with the underlying evidence, correct the data rather than the dashboard.

# 9.  Dashboard User Guide

## Section A — Workbook Structure

| Worksheet | Purpose | Editable | Maintained By |
| --- | --- | --- | --- |
| Dashboard | KPI cards, nine charts and the exception watch list | No — protected | Automatic |
| Portfolio_Master | One row per project; the single data source for everything else | Yes | PMO Analyst |
| Calc | Aggregation tables feeding the charts | Label columns only | PMO Analyst |
| Lists | Controlled value lists driving every dropdown | Inside ranges only | PMO Manager |

## Section B — KPI Definitions

| KPI | Definition | Calculation |
| --- | --- | --- |
| Active Projects | Projects in the portfolio that are neither completed nor cancelled | Count of project IDs less those with status Completed or Cancelled |
| Total in Portfolio | All projects recorded, whatever their status | Count of project IDs |
| Awaiting Approval | Projects whose overall approval decision is still outstanding | Count where Overall Approval Status is Pending |
| Awaiting Stage Gate | Projects submitted to a gate and awaiting a decision | Count where Gate Decision Status is Awaiting decision |
| Critical Governance Issues | Projects with a governance issue rated critical or high | Count where Governance Issue Level is Critical or High |
| Missing Charter | Projects without an approved project charter | Count of project IDs less those with Charter Status Approved |
| Missing Business Case | Projects without an approved business case | Count of project IDs less those with Business Case Status Approved |
| Portfolio Readiness Score | Mean initiation readiness across the portfolio | Average of the calculated readiness score across all projects |
| Projects Rated Ready | Projects scoring 85 or above on the readiness model | Count where Readiness Band is Ready |
| Projects RAG Red | Projects reporting a red overall status | Count where Overall RAG is Red |
| Approved Budget (Portfolio) | Total approved funding across the portfolio | Sum of Approved Budget |
| Forecast at Completion | Total forecast outturn across the portfolio | Sum of Forecast at Completion |

## Section C — Readiness Scoring Model

The readiness score is calculated automatically for each project from six weighted components, giving a maximum of 100.

| Component | Maximum | Scoring |
| --- | --- | --- |
| Charter status | 20 | Approved 20 · Under Review 12 · In Progress 6 · otherwise 0 |
| Business case status | 20 | Approved 20 · Under Review 12 · In Progress 6 · otherwise 0 |
| Overall approval status | 15 | Approved 15 · Not Required 15 · Approved with conditions 11 · otherwise 0 |
| Governance issue level | 15 | None 15 · Low 12 · Medium 7 · High 3 · Critical 0 |
| Initiation registers established | 15 | Yes 15 · otherwise 0 |
| Kick-off held | 15 | Yes 15 · otherwise 0 |

| Band | Score Range | Interpretation and Expected Action |
| --- | --- | --- |
| Ready | 85 – 100 | Initiation is substantively complete; the project may be presented for its gate |
| Nearly Ready | 70 – 84 | Minor gaps; present with a remediation plan and named owners |
| Gaps | 50 – 69 | Material gaps; do not present for gate approval until the gaps are closed |
| Not Ready | Below 50 | Initiation is incomplete; escalate to the sponsor and hold delivery activity |

## Section D — Charts

| Chart | Type | Source | What to Look For |
| --- | --- | --- | --- |
| Projects by Status | Column | Calc — status block | Concentration in Not Started or On Hold indicates blocked capacity |
| Projects by Project Manager | Bar | Calc — PM block | Uneven loading; a manager holding several Tier 1 projects |
| Projects by Delivery Approach | Doughnut | Calc — approach block | Whether the approach mix reflects the assessed suitability |
| Projects by Business Unit | Bar | Calc — business unit block | Demand concentration and units with no governed activity |
| Project Approval Status | Column | Calc — approval block | Volume in Pending indicates a decision bottleneck |
| Project Readiness Band | Doughnut | Calc — band block | Proportion of the portfolio not ready for its next gate |
| Projects by Governance Tier | Column | Calc — tier block | Whether tiering is being applied or defaulted |
| Stage Gate Decision Status | Bar | Calc — gate block | Backlog of gates awaiting decision |
| Governance Issue Level | Doughnut | Calc — issue block | Proportion of the portfolio carrying critical or high issues |

## Section E — Exception Watch List and Expected Response

| Exception | Governance Implication | Expected Response |
| --- | --- | --- |
| Projects with no approved Charter | Work is proceeding without authorisation | Suspend delivery activity or expedite charter approval |
| Projects with no approved Business Case | Funding committed without justification | Escalate to the Investment Board immediately |
| Projects awaiting an approval decision | Decision bottleneck consuming float | Chase the named approver against the response time standard |
| Projects awaiting a stage gate decision | Phase transition blocked | Confirm the gate date and the completeness of the submission |
| Gate submissions overdue | Governance control not being applied | Escalate to the sponsor; reschedule the gate |
| Critical or high governance issues | Control environment is compromised | Named remediation plan reported at the next portfolio meeting |
| Initiation registers not established | Risks and dependencies are unmanaged | PMO to support establishment within two weeks |
| Kick-off not held | Team not mobilised against a shared understanding | Schedule the kick-off before further delivery activity |
| Projects rated Not Ready | Project cannot pass its gate | Hold at the current phase; agree a remediation plan |
| Forecast exceeds approved budget | Investment tolerance breached or at risk | Test against tolerance; escalate if breached |
| Projects with a Red RAG status | Delivery is materially off track | Exception report to the sponsor within the standard response time |
| Projects on hold | Capacity committed but not producing value | Confirm the restart condition or release the resources |

## Section F — Reporting Cycle

| Timing | Activity | Owner | Output |
| --- | --- | --- | --- |
| Working day 1–2 | Collect project data from the registers and status reports | PMO Analyst | Portfolio_Master updated |
| Working day 3 | Verify controlled values, dates and exceptions | PMO Analyst | Verified data set |
| Working day 4 | Review the dashboard and prepare the commentary | PMO Manager | Portfolio commentary |
| Working day 5 | Issue the portfolio pack | PMO Manager | Board pack issued |
| Board meeting | Present KPIs, exceptions and required decisions | PMO Manager | Decisions and actions recorded |
| Following week | Track exception actions to closure | PMO Analyst | Updated action status |

# 10.  Approval and Authorisation

By signing below, each approver confirms that the content of this document has been reviewed, is accurate to the best of their knowledge, and is authorised for use within the project.

| Approval Role | Name | Position / Title | Signature | Date |
| --- | --- | --- | --- | --- |
| Prepared by (PMO Manager) |  |  |  |  |
| Approved by (Head of PMO) |  |  |  |  |

# 11.  Revision History

| Version | Date | Description of Change | Prepared / Revised By | Approved By |
| --- | --- | --- | --- | --- |
| 0.1 | DD-MMM-YYYY | Initial draft prepared for review | Project Manager | — |
| 0.9 | DD-MMM-YYYY | Reviewed by PMO; comments incorporated | PMO Analyst | — |
| 1.0 | 01-Sep-2026 | First approved and issued baseline | Project Manager | PMO Manager |

NOTE Rows shown in shaded italics are illustrative examples of how the revision history is completed. Replace them with the actual revision record.

# 12.  Notice and Disclaimer

PMI®, PMBOK®, PMP®, PMI-ACP® and PfMP® are registered marks of the Project Management Institute, Inc. This document is an original work product of IMTITHAL, developed in alignment with the principles, performance domains and focus areas described in the PMBOK® Guide – Eighth Edition. It is not issued, certified, endorsed or approved by PMI, and it does not reproduce PMI copyrighted text or proprietary PMI templates. Organisations remain responsible for tailoring this document to their own governance, contractual and regulatory obligations.