IMTITHAL PROJECT MANAGEMENT SYSTEM PMBOK® Guide – Eighth Edition Aligned

TOOLKIT 01  |  PROJECT INITIATION & GOVERNANCE

PROJECT BUSINESS CASE

Investment justification, options analysis and value proposition

Document Reference:  IMT-PIG-002

| DOCUMENT CONTROL |  |  |  |
| --- | --- | --- | --- |
| File Name | IMT-PIG-002_Project_Business_Case_v1.0.docx | Version | 1.0 |
| Document Owner | Project Management Office (PMO) | Document Status | Approved – Issued for Use |
| Approval Authority | Investment / Portfolio Board (or the delegated funding authority for the applicable value threshold) | Classification | Internal – Controlled Document |
| Effective Date | 01-Sep-2026 | Revision Date | 01-Sep-2026 |
| Next Review Date | 01-Sep-2027 | Review Frequency | At every stage gate, and at least every six months during delivery |

IMTITHAL Project Management System · Toolkit 01: Project Initiation & Governance This document is an original IMTITHAL work product developed in alignment with the concepts and practices of the PMBOK® Guide – Eighth Edition. PMI, PMBOK, PMP and PMI-ACP are marks of the Project Management Institute, Inc. IMTITHAL is not affiliated with, endorsed by, certified by, or approved by PMI. No PMI copyrighted text or proprietary PMI template is reproduced herein.

# 1.  Purpose

The Project Business Case establishes whether a proposed investment is justified, viable, affordable and aligned to organisational strategy. It documents the business need, evaluates credible options against defined criteria, quantifies costs and benefits over the full investment life cycle, assesses risk and sensitivity, and recommends a preferred option for funding. It is the decision instrument on which the funding authority relies, and it remains a live document that is revisited at each stage gate to confirm continued viability.

- Demonstrates that the expected value exceeds the expected cost and risk of the investment.

- Provides a transparent, auditable basis for the funding decision.

- Establishes the benefit baseline against which realisation is later measured.

- Supports portfolio prioritisation by presenting comparable value and risk information.

# 2.  When to Use

- Before any funding commitment is sought for a new project or a significant new phase.

- When an existing project requests additional funding beyond the approved envelope or beyond tolerance.

- At every stage gate, to confirm that the investment remains viable, desirable and achievable.

- When strategic priorities, market conditions or regulatory obligations change materially during delivery.

- When a project is a candidate for early termination and the continued-investment decision must be re-tested.

# 3.  Responsibility and Approval

| Governance Role | Assignment | Description of Involvement |
| --- | --- | --- |
| Responsible (prepares) | Business Owner / Project Sponsor, supported by the Project Manager, Finance Business Partner and the PMO | Prepares, populates and maintains the document; ensures accuracy and completeness of all fields. |
| Accountable (owns) | Project Sponsor | Single point of accountability for the quality, currency and control of the document. |
| Consulted | PMO, Finance, Risk, Quality, Legal/Contracts, business owners and technical disciplines as applicable | Provides subject-matter input before submission for approval. |
| Informed | Project team, affected business units, supporting functions, key external stakeholders | Receives the approved document through the controlled distribution list. |
| Approves | Investment / Portfolio Board (or the delegated funding authority for the applicable value threshold) | Formally authorises the document; approval is recorded in the Project Approval Register. |

# 4.  Required Inputs

- Organisational strategy, corporate objectives, portfolio criteria and investment appraisal standards.

- Problem or opportunity definition, demand statement, and supporting operational data.

- Market analysis, vendor information, indicative pricing and procurement advice.

- Cost estimates (capital and operating) with a stated estimate class and accuracy range.

- Benefit estimates with named benefit owners and measurement approach.

- Financial appraisal parameters: discount rate, appraisal period, tax and depreciation treatment.

- Initial risk assessment, regulatory requirements and sustainability obligations.

- Lessons learned and historical performance data from comparable initiatives.

# 5.  Required Outputs

- An approved Business Case supporting a documented investment decision.

- A recommended option with a quantified cost, benefit and risk profile.

- A baselined benefits profile feeding the Benefits Identification Register (IMT-PIG-006).

- Funding authorisation enabling the Project Charter (IMT-PIG-001) to be issued.

- Defined investment tolerances and the conditions under which the case must be revisited.

# 6.  PMBOK® Guide – Eighth Edition Alignment

This document has been designed in alignment with the following elements of the PMBOK® Guide – Eighth Edition. The alignment statement is provided for conceptual traceability only.

| Focus Area | Initiating (with re-validation during Monitoring and Controlling) |
| --- | --- |
| Performance Domains | Finance (primary); Governance, Stakeholders, Risk, Scope (supporting) |
| Guiding Principles | Focus on value · Adopt a holistic view · Integrate sustainability · Be an accountable leader |
| Tailoring Consideration | Scale the depth of financial analysis to the investment value and organisational risk appetite. Low-value or compliance-mandated investments may use a short-form case covering Sections A, B, D, E and H. Agile investments should express benefits incrementally by release rather than as a single end-state benefit. |

# 7.  Review Frequency and Approval Requirements

| Review Frequency | At every stage gate, and at least every six months during delivery |
| --- | --- |
| Review Triggers | Change of sponsor or governance structure; change of delivery approach; stage-gate decision; material change to scope, cost, schedule, benefits or risk exposure; audit or assurance finding; organisational restructuring. |
| Approval Requirements | Formal written approval by the stated Approval Authority before the document is baselined and distributed. Approval is logged in the Project Approval Register (IMT-PIG-021). |
| Change Control | Any change to an approved version requires a change request assessed through the project change control process. Minor editorial changes increment the minor version; changes affecting scope, cost, schedule, benefits or governance increment the major version and require re-approval. |
| Retention | Retained for the life of the project plus the organisational records-retention period, in the Project Information and Document Register. |

# 8.  Instructions for Completion

Complete every field. Where a field is not applicable, enter "N/A" and state the reason — never leave a field blank.

- Establish the appraisal parameters with Finance before starting: appraisal period, discount rate, treatment of inflation, tax and depreciation, and the currency and price base.

- Define the problem or opportunity in Section B without reference to any solution. A case that starts from a chosen solution cannot demonstrate that the option is the best available.

- Identify at least three credible options in Section C, always including a "do nothing / do minimum" baseline. Options that are not credible must not be included as filler.

- Score options in Section C against weighted criteria agreed in advance with the sponsor. Record the weighting rationale — post-hoc weighting invalidates the analysis.

- Build the cost profile in Section D over the full life cycle: one-off capital, implementation, transition, and recurring operating and support costs. State the estimate class and accuracy range.

- Quantify benefits in Section E. Separate cash-releasing, non-cash-releasing and non-financial benefits. Every quantified benefit requires a named owner, a baseline measure and a realisation date.

- Complete the financial appraisal in Section F. Present NPV, IRR, payback period and benefit-cost ratio, and state every assumption used in the calculation.

- Run the sensitivity and scenario analysis in Section G. Test at minimum: benefits reduced by 25%, costs increased by 25%, and a twelve-month delay in benefit realisation.

- Assess strategic, commercial, financial, management and sustainability dimensions in Section H, and record the principal risks to the investment in Section I.

- State the recommendation and the funding request in Section J, together with the tolerances within which the project may proceed without returning to the funding authority.

- Obtain Finance validation of all figures before submission. Submit to the funding authority and record the outcome in the Project Approval Register (IMT-PIG-021).

- Re-test the case at each stage gate. If the case is no longer viable, escalate for a continue / amend / terminate decision rather than allowing delivery to continue by default.

NOTE A business case that cannot survive a 25% benefit reduction is a fragile investment. Present the downside honestly — the credibility of the case, and of the PMO, depends on it.

# 9.  Template — Project Business Case

## Section A — Investment Identification

| Business Case Title | ⟨ title of the proposed investment ⟩ |
| --- | --- |
| Project Reference / ID | ⟨ PMO-issued reference ⟩ |
| Business Owner | ⟨ name and position ⟩ |
| Project Sponsor | ⟨ name and position ⟩ |
| Finance Business Partner | ⟨ name and position ⟩ |
| Portfolio / Programme | ⟨ parent portfolio or programme ⟩ |
| Investment Category | ⟨ Strategic ¦ Compliance ¦ Operational ¦ Improvement ¦ Innovation ¦ Sustaining ⟩ |
| Total Investment Requested | ⟨ currency and amount ⟩ |
| Appraisal Period | ⟨ e.g. 5 years from go-live ⟩ |
| Discount Rate Applied | ⟨ organisational rate, % ⟩ |
| Price Base / Currency | ⟨ e.g. FY2026 constant prices, SAR ⟩ |
| Document Status | ⟨ Not Started ¦ In Progress ¦ Under Review ¦ Approved ¦ Rejected ¦ On Hold ¦ Completed ¦ Cancelled ⟩ |

## Section B — Strategic Context and Business Need

| B1. Problem or Opportunity | ⟨ stated independently of any solution ⟩ |
| --- | --- |
| B2. Evidence Base | ⟨ data, metrics and sources evidencing the problem ⟩ |
| B3. Consequence of Not Investing | ⟨ quantified do-nothing impact ⟩ |
| B4. Strategic Objectives Supported | ⟨ named corporate objectives and KPIs ⟩ |
| B5. Regulatory or Compliance Obligation | ⟨ obligation and deadline, or N/A ⟩ |
| B6. Scope of the Investment | ⟨ organisational, geographic and functional boundaries ⟩ |
| B7. Key Interdependencies | ⟨ other investments this case depends upon or affects ⟩ |

## Section C — Options Analysis

### C1. Options Considered

| Option | Description | Indicative Cost | Indicative Benefit | Principal Advantages | Principal Disadvantages |
| --- | --- | --- | --- | --- | --- |
| Option 0 | Do nothing — retain current manual process | 0 | 0 | No investment required | Cost base continues to grow; compliance exposure remains |

### C2. Weighted Option Evaluation

| Evaluation Criterion | Weight % | Option 0 Score | Option 1 Score | Option 2 Score | Weighting Rationale |
| --- | --- | --- | --- | --- | --- |
| Strategic alignment | 25 | 1 | 4 | 5 | Board has designated digital service delivery as the primary FY26 objective |

### C3. Recommended Option and Rationale

| Recommended Option | ⟨ option reference ⟩ |
| --- | --- |
| Rationale for Recommendation | ⟨ why this option best balances value, cost, risk and deliverability ⟩ |
| Options Rejected and Why | ⟨ brief justification for each rejected option ⟩ |

## Section D — Whole-Life Cost Profile

| Cost Category | Type | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Software licences | CAPEX | 450,000 | 90,000 | 90,000 | 90,000 | 90,000 | 90,000 | 900,000 |

| Estimate Class and Accuracy Range | ⟨ e.g. Class 3, −15% / +25% ⟩ |
| --- | --- |
| Basis of Estimate | ⟨ source of estimating data and method ⟩ |
| Contingency Included | ⟨ amount and basis ⟩ |
| Costs Excluded from this Case | ⟨ explicit exclusions ⟩ |

## Section E — Benefits Profile

| Ref | Benefit Description | Type | Benefit Owner | Baseline Measure | Target Measure | Annual Value | First Realisation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| BEN-01 | Reduced manual processing effort | Cash-releasing | Operations Manager | 4.2 FTE | 1.5 FTE | 285,000 | Q3 FY27 |

NOTE Benefit types: Cash-releasing (removes cost from the budget) · Non-cash-releasing (releases capacity without reducing budget) · Revenue-generating · Risk / compliance avoidance · Non-financial (quality, experience, sustainability, reputation).

## Section F — Financial Appraisal

| Financial Measure | Result | Organisational Threshold | Meets Threshold (Yes / No) | Comment |
| --- | --- | --- | --- | --- |

| Financial Measure | Result | Organisational Threshold | Meets Threshold | Comment |
| --- | --- | --- | --- | --- |
| Net Present Value (NPV) |  |  |  |  |
| Internal Rate of Return (IRR) |  |  |  |  |
| Payback Period |  |  |  |  |
| Benefit–Cost Ratio |  |  |  |  |
| Total Cost of Ownership |  |  |  |  |
| Annual Recurring Cost after Go-Live |  |  |  |  |

## Section G — Sensitivity and Scenario Analysis

| Scenario | Assumption Varied | Revised NPV | Revised Payback | Investment Still Viable? | Mitigating Action |
| --- | --- | --- | --- | --- | --- |
| Downside | Benefits reduced by 25% |  |  | Yes / No | Phase release to protect early benefit capture |

## Section H — Five-Dimension Case Assessment

| Dimension | Question Addressed | Assessment | Evidence / Reference |
| --- | --- | --- | --- |

| Dimension | Question Addressed | Assessment | Evidence / Reference |
| --- | --- | --- | --- |
| Strategic | Is the investment aligned and necessary? |  |  |
| Economic | Does it deliver best value for money? |  |  |
| Commercial | Is it procurable and contractually sound? |  |  |
| Financial | Is it affordable and funded? |  |  |
| Management | Is it deliverable with available capability? |  |  |
| Sustainability | Are ESG impacts understood and managed? |  |  |

## Section I — Principal Risks to the Investment

| Ref | Investment Risk | Probability | Financial Impact | Risk Response | Owner |
| --- | --- | --- | --- | --- | --- |
| IR-01 | Benefit realisation delayed by operational readiness | Medium | Up to 180,000 in year 1 | Establish readiness gate before go-live | Business Owner |

## Section J — Recommendation, Funding Request and Tolerances

| J1. Recommendation to the Funding Authority | ⟨ Approve ¦ Approve with conditions ¦ Defer ¦ Reject ⟩ |
| --- | --- |
| J2. Funding Requested at this Decision Point | ⟨ amount and stage covered ⟩ |
| J3. Conditions of Approval | ⟨ conditions that must be satisfied ⟩ |
| J4. Cost Tolerance | ⟨ e.g. ±10% before re-approval is required ⟩ |
| J5. Schedule Tolerance | ⟨ e.g. ±1 month on gate dates ⟩ |
| J6. Benefit Tolerance | ⟨ e.g. −10% of forecast benefit ⟩ |
| J7. Next Review Point | ⟨ gate or date at which the case is re-tested ⟩ |
| J8. Consequence of Breaching Tolerance | ⟨ escalation and re-approval requirement ⟩ |

# 10.  Approval and Authorisation

By signing below, each approver confirms that the content of this document has been reviewed, is accurate to the best of their knowledge, and is authorised for use within the project.

| Approval Role | Name | Position / Title | Signature | Date |
| --- | --- | --- | --- | --- |
| Prepared by (Business Owner) |  |  |  |  |
| Financially validated by (Finance Business Partner) |  |  |  |  |
| Reviewed by (PMO Manager) |  |  |  |  |
| Recommended by (Project Sponsor) |  |  |  |  |
| Approved by (Investment Board Chair) |  |  |  |  |

# 11.  Revision History

| Version | Date | Description of Change | Prepared / Revised By | Approved By |
| --- | --- | --- | --- | --- |
| 0.1 | DD-MMM-YYYY | Initial draft prepared for review | Project Manager | — |
| 0.9 | DD-MMM-YYYY | Reviewed by PMO; comments incorporated | PMO Analyst | — |
| 1.0 | 01-Sep-2026 | First approved and issued baseline | Project Manager | Investment / Portfolio Board (or the delegated funding authority for the applicable value threshold) |

NOTE Rows shown in shaded italics are illustrative examples of how the revision history is completed. Replace them with the actual revision record.

# 12.  Notice and Disclaimer

PMI®, PMBOK®, PMP®, PMI-ACP® and PfMP® are registered marks of the Project Management Institute, Inc. This document is an original work product of IMTITHAL, developed in alignment with the principles, performance domains and focus areas described in the PMBOK® Guide – Eighth Edition. It is not issued, certified, endorsed or approved by PMI, and it does not reproduce PMI copyrighted text or proprietary PMI templates. Organisations remain responsible for tailoring this document to their own governance, contractual and regulatory obligations.