IMTITHAL PROJECT MANAGEMENT SYSTEM PMBOK® Guide – Eighth Edition Aligned

TOOLKIT 01  |  PROJECT INITIATION & GOVERNANCE

PROJECT BENEFITS REALISATION PLAN

Plan for enabling, measuring, tracking and sustaining benefit realisation

Document Reference:  IMT-PIG-007

| DOCUMENT CONTROL |  |  |  |
| --- | --- | --- | --- |
| File Name | IMT-PIG-007_Project_Benefits_Realisation_Plan_v1.0.docx | Version | 1.0 |
| Document Owner | Project Management Office (PMO) | Document Status | Approved – Issued for Use |
| Approval Authority | Project Sponsor, with endorsement from each named Benefit Owner | Classification | Internal – Controlled Document |
| Effective Date | 01-Sep-2026 | Revision Date | 01-Sep-2026 |
| Next Review Date | 01-Sep-2027 | Review Frequency | Monthly during delivery; at every stage gate; and at each post-implementation benefit review until full realisation is confirmed |

IMTITHAL Project Management System · Toolkit 01: Project Initiation & Governance This document is an original IMTITHAL work product developed in alignment with the concepts and practices of the PMBOK® Guide – Eighth Edition. PMI, PMBOK, PMP and PMI-ACP are marks of the Project Management Institute, Inc. IMTITHAL is not affiliated with, endorsed by, certified by, or approved by PMI. No PMI copyrighted text or proprietary PMI template is reproduced herein.

# 1.  Purpose

The Benefits Realisation Plan sets out how the benefits identified in the Benefits Identification Register will actually be achieved, measured, tracked and sustained. It defines the enabling outputs and business changes required, the realisation timeline, the measurement regime, the governance of benefit reporting, and the transfer of accountability from the project to the operational owner at handover. It is the instrument that prevents a project from being declared successful on the basis of delivered outputs alone.

- Connects delivered outputs to the business change needed to convert them into outcomes.

- Establishes when each benefit will begin to be realised and when it reaches full run-rate.

- Defines who measures what, how often, and to whom results are reported.

- Governs the handover of benefit accountability to the operational owner after project closure.

# 2.  When to Use

- During initiation and planning, once the Benefits Identification Register has been approved.

- Before each stage gate, to confirm that the realisation trajectory remains credible.

- At handover, to formally transfer benefit accountability to the operational owner.

- During the post-implementation and benefit-tracking period after project closure.

- When an approved change alters the benefit profile, timing or ownership.

# 3.  Responsibility and Approval

| Governance Role | Assignment | Description of Involvement |
| --- | --- | --- |
| Responsible (prepares) | Business Owner, supported by the Project Manager and the Change Manager | Prepares, populates and maintains the document; ensures accuracy and completeness of all fields. |
| Accountable (owns) | Project Sponsor until closure; the named Benefit Owner thereafter | Single point of accountability for the quality, currency and control of the document. |
| Consulted | PMO, Finance, Risk, Quality, Legal/Contracts, business owners and technical disciplines as applicable | Provides subject-matter input before submission for approval. |
| Informed | Project team, affected business units, supporting functions, key external stakeholders | Receives the approved document through the controlled distribution list. |
| Approves | Project Sponsor, with endorsement from each named Benefit Owner | Formally authorises the document; approval is recorded in the Project Approval Register. |

# 4.  Required Inputs

- Approved Benefits Identification Register (IMT-PIG-006).

- Approved Business Case with the financial appraisal and benefit assumptions.

- Project Objectives and Success Criteria Form (IMT-PIG-005).

- Project schedule and release plan, providing the timing of enabling outputs.

- Organisational change impact assessment and change readiness information.

- Operational performance reporting capability and available data sources.

# 5.  Required Outputs

- An approved realisation plan with a benefit-by-benefit realisation profile and timeline.

- A defined measurement and reporting regime with named measurement owners.

- A benefit handover and sustainment arrangement effective from project closure.

- Benefit review checkpoints scheduled through and beyond the project life cycle.

- Inputs to the post-implementation review and to portfolio benefit reporting.

# 6.  PMBOK® Guide – Eighth Edition Alignment

This document has been designed in alignment with the following elements of the PMBOK® Guide – Eighth Edition. The alignment statement is provided for conceptual traceability only.

| Focus Area | Planning, Monitoring and Controlling, and Closing |
| --- | --- |
| Performance Domains | Finance (primary); Governance, Stakeholders, Scope, Resources (supporting) |
| Guiding Principles | Focus on value · Adopt a holistic view · Be an accountable leader · Integrate sustainability |
| Tailoring Consideration | Agile and hybrid delivery should align the realisation profile to release boundaries so that benefit is recognised incrementally. For long-tail benefits, extend the tracking period beyond closure and assign a permanent operational owner in Section G. |

# 7.  Review Frequency and Approval Requirements

| Review Frequency | Monthly during delivery; at every stage gate; and at each post-implementation benefit review until full realisation is confirmed |
| --- | --- |
| Review Triggers | Change of sponsor or governance structure; change of delivery approach; stage-gate decision; material change to scope, cost, schedule, benefits or risk exposure; audit or assurance finding; organisational restructuring. |
| Approval Requirements | Formal written approval by the stated Approval Authority before the document is baselined and distributed. Approval is logged in the Project Approval Register (IMT-PIG-021). |
| Change Control | Any change to an approved version requires a change request assessed through the project change control process. Minor editorial changes increment the minor version; changes affecting scope, cost, schedule, benefits or governance increment the major version and require re-approval. |
| Retention | Retained for the life of the project plus the organisational records-retention period, in the Project Information and Document Register. |

# 8.  Instructions for Completion

Complete every field. Where a field is not applicable, enter "N/A" and state the reason — never leave a field blank.

- Build the plan directly from the approved Benefits Identification Register. Every benefit in the register must appear in this plan, and no benefit may appear here that is not in the register.

- For each benefit, complete the benefit map in Section B: enabling output, required business change, intermediate outcome, and the end benefit. A missing business change is the strongest predictor of an unrealised benefit.

- Build the realisation profile in Section C. Record when realisation starts, the ramp-up trajectory, and the date full run-rate is achieved. Realisation is rarely instantaneous at go-live and should not be planned as though it were.

- Define the measurement regime in Section D. Confirm that each data source exists and is accessible before committing to the measure — retro-fitting measurement after go-live is expensive and often impossible.

- Set the benefit review schedule in Section E, including reviews that fall after project closure. Assign a governance body to each review.

- Record the change and adoption activities in Section F that are required to convert outputs into outcomes: training, communication, process change, role change, incentive alignment and decommissioning of the old way of working.

- Complete Section G before handover. Benefit accountability must transfer to a named operational owner with an agreed tracking and reporting arrangement, otherwise tracking stops at closure.

- Record risks to realisation in Section H and ensure each is reflected in the Project Risk Register with a named owner.

- Obtain endorsement from every benefit owner. An owner who will not endorse the plan will not deliver the benefit.

- Track actual against forecast at each review in Section I, and escalate a forecast shortfall through governance as soon as it is identified rather than at the end of the tracking period.

NOTE Benefit realisation almost always extends beyond project closure. Ensure that Section G is complete and formally accepted before the project is closed, otherwise accountability lapses at exactly the point where realisation begins.

# 9.  Template — Project Benefits Realisation Plan

## Section A — Plan Identification

| Project Name |  |
| --- | --- |
| Project Reference / ID |  |
| Business Owner |  |
| Project Sponsor |  |
| Benefit Tracking Period | ⟨ e.g. go-live + 24 months ⟩ |
| Total Forecast Annual Benefit | ⟨ currency and amount ⟩ |
| Plan Version and Date |  |
| Plan Status | ⟨ Not Started ¦ In Progress ¦ Under Review ¦ Approved ¦ Rejected ¦ On Hold ¦ Completed ¦ Cancelled ⟩ |

## Section B — Benefit Map: Output to Outcome to Benefit

| Benefit Ref | Enabling Output (project deliverable) | Required Business Change | Intermediate Outcome | End Benefit | Benefit Owner |
| --- | --- | --- | --- | --- | --- |
| BEN-01 | Automated onboarding workflow in production | Roles redesigned; staff retrained; manual process withdrawn | Cases processed without manual re-keying | Onboarding effort reduced by 2.7 FTE | Ops Manager |

## Section C — Realisation Profile

| Benefit Ref | Realisation Start | Ramp-Up Period | Full Run-Rate Date | Yr 1 Forecast | Yr 2 Forecast | Yr 3 Forecast | Cumulative Forecast |
| --- | --- | --- | --- | --- | --- | --- | --- |
| BEN-01 | Q3 FY27 | 4 months | Q1 FY28 | 95,000 | 285,000 | 285,000 | 665,000 |

## Section D — Measurement and Reporting Regime

| Benefit Ref | Measure | Baseline Value and Date | Data Source | Frequency | Measurement Owner | Reported To | Report Format |
| --- | --- | --- | --- | --- | --- | --- | --- |

## Section E — Benefit Review Schedule

| Review | Timing | Scope of Review | Chaired By | Attendees | Output |
| --- | --- | --- | --- | --- | --- |
| BR-1 | Go-live + 3 months | Early indicator review; confirm baseline shift | Business Owner | Benefit owners, PM, Finance | Benefit status report |

## Section F — Change and Adoption Activities

| Ref | Activity Required to Enable Realisation | Type | Target Group | Owner | Due | Status |
| --- | --- | --- | --- | --- | --- | --- |
| CA-01 | Withdraw the legacy manual process and remove system access | Process change | Onboarding team | Ops Manager | Go-live + 2 wk | Not Started |

## Section G — Benefit Handover and Sustainment

| G1. Handover Date | ⟨ date benefit accountability transfers to operations ⟩ |
| --- | --- |
| G2. Receiving Operational Owner | ⟨ name and position ⟩ |
| G3. Ongoing Tracking Arrangement | ⟨ who tracks, how often, using what report ⟩ |
| G4. Governance Body Receiving Reports | ⟨ body and cadence after closure ⟩ |
| G5. Sustainment Actions Required | ⟨ actions needed to prevent benefit decay ⟩ |
| G6. Conditions for Ceasing Tracking | ⟨ when tracking may formally stop ⟩ |
| G7. Handover Acceptance | ⟨ signature and date of the receiving owner ⟩ |

## Section H — Risks to Benefit Realisation

| Ref | Risk to Realisation | Benefit(s) Affected | Probability | Impact on Benefit | Response | Owner | Risk Register Ref |
| --- | --- | --- | --- | --- | --- | --- | --- |
| BR-01 | Legacy process not withdrawn; staff revert to old method | BEN-01 | Medium | Up to 60% of forecast | Withdraw system access at go-live +2 weeks | Ops Manager | RSK-011 |

## Section I — Realisation Tracking Log

| Review Date | Benefit Ref | Forecast to Date | Actual to Date | Variance | RAG | Explanation | Corrective Action | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

# 10.  Approval and Authorisation

By signing below, each approver confirms that the content of this document has been reviewed, is accurate to the best of their knowledge, and is authorised for use within the project.

| Approval Role | Name | Position / Title | Signature | Date |
| --- | --- | --- | --- | --- |
| Prepared by (Business Owner) |  |  |  |  |
| Endorsed by (Benefit Owner) |  |  |  |  |
| Reviewed by (PMO) |  |  |  |  |
| Approved by (Project Sponsor) |  |  |  |  |

# 11.  Revision History

| Version | Date | Description of Change | Prepared / Revised By | Approved By |
| --- | --- | --- | --- | --- |
| 0.1 | DD-MMM-YYYY | Initial draft prepared for review | Project Manager | — |
| 0.9 | DD-MMM-YYYY | Reviewed by PMO; comments incorporated | PMO Analyst | — |
| 1.0 | 01-Sep-2026 | First approved and issued baseline | Project Manager | Project Sponsor, with endorsement from each named Benefit Owner |

NOTE Rows shown in shaded italics are illustrative examples of how the revision history is completed. Replace them with the actual revision record.

# 12.  Notice and Disclaimer

PMI®, PMBOK®, PMP®, PMI-ACP® and PfMP® are registered marks of the Project Management Institute, Inc. This document is an original work product of IMTITHAL, developed in alignment with the principles, performance domains and focus areas described in the PMBOK® Guide – Eighth Edition. It is not issued, certified, endorsed or approved by PMI, and it does not reproduce PMI copyrighted text or proprietary PMI templates. Organisations remain responsible for tailoring this document to their own governance, contractual and regulatory obligations.