IMTITHAL PROJECT MANAGEMENT SYSTEM PMBOK® Guide – Eighth Edition Aligned

TOOLKIT 01  |  PROJECT INITIATION & GOVERNANCE

PROJECT GOVERNANCE FRAMEWORK

Organisational framework for project oversight, control and decision rights

Document Reference:  IMT-PIG-008

| DOCUMENT CONTROL |  |  |  |
| --- | --- | --- | --- |
| File Name | IMT-PIG-008_Project_Governance_Framework_v1.0.docx | Version | 1.0 |
| Document Owner | Project Management Office (PMO) | Document Status | Approved – Issued for Use |
| Approval Authority | Executive Management / Portfolio Board | Classification | Internal – Controlled Document |
| Effective Date | 01-Sep-2026 | Revision Date | 01-Sep-2026 |
| Next Review Date | 01-Sep-2027 | Review Frequency | Annually, and following any material organisational restructuring, audit finding or change to the delegation of authority policy |

IMTITHAL Project Management System · Toolkit 01: Project Initiation & Governance This document is an original IMTITHAL work product developed in alignment with the concepts and practices of the PMBOK® Guide – Eighth Edition. PMI, PMBOK, PMP and PMI-ACP are marks of the Project Management Institute, Inc. IMTITHAL is not affiliated with, endorsed by, certified by, or approved by PMI. No PMI copyrighted text or proprietary PMI template is reproduced herein.

# 1.  Purpose

The Project Governance Framework defines how projects are directed and controlled within the organisation. It establishes the governance tiers applied according to project value, complexity and risk; the governance bodies and their terms of reference; the stage-gate model and its decision criteria; the delegated decision and financial authority; the escalation, assurance and reporting regime; and the standards of conduct, transparency and accountability expected of everyone involved. It is the master governance reference from which project-specific governance arrangements are derived.

- Establishes consistent, proportionate oversight across the whole project portfolio.

- Defines who decides what, at which value threshold, and on what evidence.

- Provides the stage-gate model and the criteria applied at each gate.

- Sets the assurance, escalation and transparency standards that protect organisational value.

# 2.  When to Use

- As the standing reference for all projects; applied at initiation to determine the governance tier.

- When establishing the governance arrangements for a new project or programme.

- When a project changes tier as a result of a change in value, complexity or risk exposure.

- During governance reviews, assurance activities and internal audit.

- When onboarding new sponsors, project managers or steering committee members.

# 3.  Responsibility and Approval

| Governance Role | Assignment | Description of Involvement |
| --- | --- | --- |
| Responsible (prepares) | PMO Manager | Prepares, populates and maintains the document; ensures accuracy and completeness of all fields. |
| Accountable (owns) | Head of PMO / Portfolio Director | Single point of accountability for the quality, currency and control of the document. |
| Consulted | Finance, Internal Audit, Risk, Legal and Compliance, business unit leadership | Provides subject-matter input before submission for approval. |
| Informed | All project sponsors, project managers, steering committee members and project teams | Receives the approved document through the controlled distribution list. |
| Approves | Executive Management / Portfolio Board | Formally authorises the document; approval is recorded in the Project Approval Register. |

# 4.  Required Inputs

- Organisational strategy, delegation of authority policy and financial regulations.

- Corporate risk appetite statement and risk management framework.

- Regulatory, contractual and audit requirements applicable to project delivery.

- Existing organisational project management methodology and maturity assessment.

- Lessons learned, audit findings and assurance recommendations from prior projects.

# 5.  Required Outputs

- An approved organisational governance framework applicable to all projects.

- A defined governance tiering model with threshold criteria.

- Terms of reference for each governance body.

- A defined stage-gate model with entry, exit and decision criteria.

- A published escalation, assurance and reporting regime.

# 6.  PMBOK® Guide – Eighth Edition Alignment

This document has been designed in alignment with the following elements of the PMBOK® Guide – Eighth Edition. The alignment statement is provided for conceptual traceability only.

| Focus Area | Applies across all focus areas; established before Initiating |
| --- | --- |
| Performance Domains | Governance (primary); Stakeholders, Risk, Finance (supporting) |
| Guiding Principles | Be an accountable leader · Adopt a holistic view · Focus on value · Build an empowered culture · Integrate sustainability |
| Tailoring Consideration | The framework itself is not tailored per project; instead the framework defines the tiers within which projects are tailored. Project-specific tailoring is recorded in the Tailoring Assessment (IMT-PIG-017) and must remain within the boundaries set here. |

# 7.  Review Frequency and Approval Requirements

| Review Frequency | Annually, and following any material organisational restructuring, audit finding or change to the delegation of authority policy |
| --- | --- |
| Review Triggers | Change of sponsor or governance structure; change of delivery approach; stage-gate decision; material change to scope, cost, schedule, benefits or risk exposure; audit or assurance finding; organisational restructuring. |
| Approval Requirements | Approved by Executive Management or the Portfolio Board. Any deviation applied to an individual project requires a documented, sponsor-approved waiver recorded in the Project Approval Register. |
| Change Control | Any change to an approved version requires a change request assessed through the project change control process. Minor editorial changes increment the minor version; changes affecting scope, cost, schedule, benefits or governance increment the major version and require re-approval. |
| Retention | Retained for the life of the project plus the organisational records-retention period, in the Project Information and Document Register. |

# 8.  Instructions for Completion

Complete every field. Where a field is not applicable, enter "N/A" and state the reason — never leave a field blank.

- Confirm the organisational delegation of authority policy and financial regulations first. Project governance thresholds must be consistent with them, never in conflict.

- Define the governance tiering criteria in Section B using value, complexity, risk exposure, strategic significance and regulatory sensitivity. Test the criteria against the current portfolio to confirm a sensible distribution.

- Define each governance body in Section C with its purpose, membership, quorum, cadence, decision rights and reporting obligations. A body without defined decision rights becomes an information forum.

- Define the stage-gate model in Section D. For each gate state the entry criteria, the evidence required, the decision options and the authority that decides.

- Define the decision and financial authority thresholds in Section E, ensuring that every threshold has an unambiguous escalation point above it.

- Define the escalation regime in Section F, including tolerance breaches and the maximum time within which an escalation must receive a response.

- Define the assurance regime in Section G: what is assured, by whom, at what frequency, and how findings are tracked to closure.

- Define the reporting regime in Section H, specifying report, producer, recipient, frequency and content standard.

- Publish the framework, brief all sponsors and project managers, and apply it from the effective date. Record the applicable tier for every project in the portfolio register.

- Review annually and after any material organisational change; track amendments through the revision history.

# 9.  Template — Project Governance Framework

## Section A — Framework Scope and Governance Principles

| A1. Scope of Application | ⟨ which projects, programmes and business units this framework governs ⟩ |
| --- | --- |
| A2. Effective Date | ⟨ DD-MMM-YYYY ⟩ |
| A3. Related Policies | ⟨ delegation of authority, financial regulations, risk framework, procurement policy ⟩ |
| A4. Framework Owner | ⟨ role accountable for the framework ⟩ |
| A5. Exemptions | ⟨ categories of work explicitly outside this framework ⟩ |

| Governance Principle | Definition Applied in this Organisation | How Compliance is Evidenced |
| --- | --- | --- |
| Accountability | Every project has a single accountable sponsor and a single accountable project manager | Charter signature; organisation chart |
| Proportionality | Governance effort is proportionate to value, complexity and risk | Tier assignment; tailoring assessment |
| Transparency | Status is reported honestly, on time, and without filtering | Reporting compliance; assurance review |
| Value focus | Continued investment is justified at every gate | Business case re-test at each gate |
| Timely decision-making | Decisions are made within defined response times at the right level | Decision log; escalation response times |
| Segregation of duties | Those who deliver do not approve their own work | Approval register; assurance sampling |
| Empowerment | Teams are authorised to decide within defined limits | Authority matrix; decision-making matrix |
| Sustainability | Environmental, social and governance impacts are assessed and managed | Business case Section H; gate criteria |

## Section B — Governance Tiering Model

| Tier | Value Threshold | Complexity / Risk | Governing Body | Gate Regime | Reporting Cadence |
| --- | --- | --- | --- | --- | --- |
| Tier 1 | Above the major-project threshold | High complexity, high risk, strategic or regulated | Portfolio Board plus Project Steering Committee | Full gate model G0–G5, independent assurance at G2 and G4 | Monthly to the Board; fortnightly to the Steering Committee |
| Tier 2 | Between the minor and major thresholds | Moderate complexity and risk | Project Steering Committee | Gates G1, G3 and G5; PMO assurance | Monthly |
| Tier 3 | Below the minor threshold | Low complexity, low risk, single business unit | Sponsor with PMO oversight | Combined initiation gate and closure gate | Monthly summary |
| Fast-track | Any value where a regulatory or emergency driver applies | Time-critical | Sponsor with retrospective Board ratification | Condensed gates with mandatory retrospective review | Weekly until stabilised |

| Tier Determination Method | ⟨ how the tier is calculated and who confirms it ⟩ |
| --- | --- |
| Tier Review Trigger | ⟨ circumstances requiring the tier to be re-assessed ⟩ |
| Tier Change Authority | ⟨ who may change a project tier ⟩ |

## Section C — Governance Bodies and Terms of Reference

| Governance Body | Purpose | Chair | Core Membership | Quorum | Cadence | Principal Decision Rights |
| --- | --- | --- | --- | --- | --- | --- |
| Project Steering Committee | Direct the project and decide at gates | Project Sponsor | Business owner, PM, PMO, Finance, key function heads | 3 incl. chair | Monthly | Gate decisions; change within tolerance; risk escalation acceptance |

## Section D — Stage-Gate Model

| Gate | Gate Name | Entry Criteria | Evidence Required | Decision Options | Decision Authority |
| --- | --- | --- | --- | --- | --- |
| G0 | Concept / Screening | Proposal submitted and complete | Project Proposal (IMT-PIG-003); prioritisation score | Progress / Defer / Merge / Reject | Portfolio Board |
| G1 | Initiation / Authorisation | Business Case approved; funding released | Business Case, Charter, Initiation Checklist, initiation registers | Approve / Approve with conditions / Hold / Reject | Sponsor (Tier 2–3); Portfolio Board (Tier 1) |
| G2 | Planning / Baseline | Project Management Plan complete and integrated | Baselined scope, schedule, budget; risk register; approach and tailoring | Baseline / Re-plan / Hold / Terminate | Steering Committee |
| G3 | Delivery Readiness | Design complete; build authorised; readiness assessed | Design sign-off; procurement in place; updated business case | Proceed / Conditional / Hold / Terminate | Steering Committee |
| G4 | Deployment Readiness | Solution tested and accepted; operations ready | Test evidence; operational readiness assessment; cutover plan | Deploy / Conditional deploy / Defer / Abort | Steering Committee and receiving function |
| G5 | Closure and Handover | Deliverables accepted; handover complete | Acceptance records; benefits handover; closure report; lessons learned | Close / Close with actions / Retain open | Sponsor and Steering Committee |

NOTE Agile and hybrid projects retain the same gate decision points but satisfy the evidence requirements through release-level artefacts — product vision, prioritised backlog, definition of done, release readiness evidence and increment demonstrations — rather than through single fixed baselines.

## Section E — Decision and Financial Authority Thresholds

| Decision Type | Project Manager | Project Sponsor | Steering Committee | Portfolio Board | Executive Management |
| --- | --- | --- | --- | --- | --- |
| Expenditure commitment | Up to 5% of budget | Up to 15% of budget | Up to 25% of budget | Up to approved envelope | Above envelope |

## Section F — Escalation Regime

| Escalation Trigger | Escalate To | Escalation Route | Maximum Response Time | Record In |
| --- | --- | --- | --- | --- |
| Forecast cost breach of tolerance | Project Sponsor | Exception report within 2 working days | 5 working days | Decision log; approval register |

## Section G — Assurance Regime

| Assurance Activity | Applied To | Performed By | Frequency / Trigger | Output | Findings Tracked In |
| --- | --- | --- | --- | --- | --- |
| Gate assurance review | Tier 1 at G2 and G4 | Independent assurance reviewer | Before each applicable gate | Assurance report with RAG rating | PMO assurance action log |

## Section H — Reporting Regime

| Report | Produced By | Recipient | Frequency | Due | Minimum Content |
| --- | --- | --- | --- | --- | --- |
| Project status report | Project Manager | Steering Committee, PMO | Monthly | 3rd working day | Progress, RAG, cost and schedule variance, risks, issues, decisions required |

## Section I — Governance Compliance and Breach

| I1. Compliance Monitoring Method | ⟨ how compliance with this framework is monitored ⟩ |
| --- | --- |
| I2. Consequences of Non-Compliance | ⟨ consequences applied where governance obligations are not met ⟩ |
| I3. Waiver Process | ⟨ how a deviation is requested, assessed and approved ⟩ |
| I4. Waiver Approval Authority | ⟨ who may approve a deviation from this framework ⟩ |
| I5. Framework Improvement Route | ⟨ how lessons and audit findings amend this framework ⟩ |

# 10.  Approval and Authorisation

By signing below, each approver confirms that the content of this document has been reviewed, is accurate to the best of their knowledge, and is authorised for use within the project.

| Approval Role | Name | Position / Title | Signature | Date |
| --- | --- | --- | --- | --- |
| Prepared by (PMO Manager) |  |  |  |  |
| Reviewed by (Internal Audit / Risk) |  |  |  |  |
| Recommended by (Head of PMO) |  |  |  |  |
| Approved by (Executive Management) |  |  |  |  |

# 11.  Revision History

| Version | Date | Description of Change | Prepared / Revised By | Approved By |
| --- | --- | --- | --- | --- |
| 0.1 | DD-MMM-YYYY | Initial draft prepared for review | Project Manager | — |
| 0.9 | DD-MMM-YYYY | Reviewed by PMO; comments incorporated | PMO Analyst | — |
| 1.0 | 01-Sep-2026 | First approved and issued baseline | Project Manager | Executive Management / Portfolio Board |

NOTE Rows shown in shaded italics are illustrative examples of how the revision history is completed. Replace them with the actual revision record.

# 12.  Notice and Disclaimer

PMI®, PMBOK®, PMP®, PMI-ACP® and PfMP® are registered marks of the Project Management Institute, Inc. This document is an original work product of IMTITHAL, developed in alignment with the principles, performance domains and focus areas described in the PMBOK® Guide – Eighth Edition. It is not issued, certified, endorsed or approved by PMI, and it does not reproduce PMI copyrighted text or proprietary PMI templates. Organisations remain responsible for tailoring this document to their own governance, contractual and regulatory obligations.