IMTITHAL PROJECT MANAGEMENT SYSTEM PMBOK® Guide – Eighth Edition Aligned

TOOLKIT 01  |  PROJECT INITIATION & GOVERNANCE

PROJECT DECISION-MAKING MATRIX

Allocation of decision rights, thresholds and response times

Document Reference:  IMT-PIG-010

| DOCUMENT CONTROL |  |  |  |
| --- | --- | --- | --- |
| File Name | IMT-PIG-010_Project_Decision_Making_Matrix_v1.0.docx | Version | 1.0 |
| Document Owner | Project Management Office (PMO) | Document Status | Approved – Issued for Use |
| Approval Authority | Project Sponsor; endorsed by the PMO for consistency with the Governance Framework | Classification | Internal – Controlled Document |
| Effective Date | 01-Sep-2026 | Revision Date | 01-Sep-2026 |
| Next Review Date | 01-Sep-2027 | Review Frequency | At every stage gate, and whenever the governance structure or delegated authority changes |

IMTITHAL Project Management System · Toolkit 01: Project Initiation & Governance This document is an original IMTITHAL work product developed in alignment with the concepts and practices of the PMBOK® Guide – Eighth Edition. PMI, PMBOK, PMP and PMI-ACP are marks of the Project Management Institute, Inc. IMTITHAL is not affiliated with, endorsed by, certified by, or approved by PMI. No PMI copyrighted text or proprietary PMI template is reproduced herein.

# 1.  Purpose

The Decision-Making Matrix records, for every recurring decision type in the project, who proposes it, who is consulted, who decides, who may veto, who is informed, and within what time the decision must be made. It converts governance intent into an operational instrument that the team can consult daily. Its purpose is to eliminate the two most costly governance failures: decisions taken by people without the authority to take them, and decisions that no one takes at all.

- Assigns a single decision-maker to every recurring decision type.

- Sets a maximum response time so that decisions do not become silent bottlenecks.

- Distinguishes decision rights from consultation rights and from veto rights.

- Provides the reference against which the decision log is audited.

# 2.  When to Use

- During initiation, once the governance structure has been established.

- Whenever a decision is contested, delayed or taken at the wrong level.

- When a new decision type emerges that the matrix does not yet cover.

- At each stage gate, to confirm that decision rights remain appropriate for the coming phase.

- When onboarding new team members, sponsors or steering committee members.

# 3.  Responsibility and Approval

| Governance Role | Assignment | Description of Involvement |
| --- | --- | --- |
| Responsible (prepares) | Project Manager | Prepares, populates and maintains the document; ensures accuracy and completeness of all fields. |
| Accountable (owns) | Project Sponsor | Single point of accountability for the quality, currency and control of the document. |
| Consulted | PMO, Finance, Risk, Quality, Legal/Contracts, business owners and technical disciplines as applicable | Provides subject-matter input before submission for approval. |
| Informed | Project team, affected business units, supporting functions, key external stakeholders | Receives the approved document through the controlled distribution list. |
| Approves | Project Sponsor; endorsed by the PMO for consistency with the Governance Framework | Formally authorises the document; approval is recorded in the Project Approval Register. |

# 4.  Required Inputs

- Project Governance Framework (IMT-PIG-008) and Governance Structure (IMT-PIG-009).

- Organisational delegation of authority policy and financial regulations.

- Project Charter, in particular the project manager authority section.

- Authority Matrix (IMT-PIG-011) and Roles and Responsibilities Matrix (IMT-PIG-012).

- Lessons learned regarding decision bottlenecks on comparable projects.

# 5.  Required Outputs

- An approved matrix of decision rights covering all recurring decision types.

- Defined maximum response times and default positions where a decision is not taken.

- A structured project decision log.

- Clear escalation routes when a decision cannot be taken at the assigned level.

# 6.  PMBOK® Guide – Eighth Edition Alignment

This document has been designed in alignment with the following elements of the PMBOK® Guide – Eighth Edition. The alignment statement is provided for conceptual traceability only.

| Focus Area | Initiating and Planning; applied through Executing and Monitoring and Controlling |
| --- | --- |
| Performance Domains | Governance (primary); Stakeholders, Resources, Risk (supporting) |
| Guiding Principles | Be an accountable leader · Build an empowered culture · Focus on value |
| Tailoring Consideration | Agile projects allocate product-scope and prioritisation decisions to the product owner with an explicit escalation threshold, and delivery-method decisions to the team. Hybrid projects must state clearly which decision types follow the adaptive route and which follow the predictive change-control route. |

# 7.  Review Frequency and Approval Requirements

| Review Frequency | At every stage gate, and whenever the governance structure or delegated authority changes |
| --- | --- |
| Review Triggers | Change of sponsor or governance structure; change of delivery approach; stage-gate decision; material change to scope, cost, schedule, benefits or risk exposure; audit or assurance finding; organisational restructuring. |
| Approval Requirements | Formal written approval by the stated Approval Authority before the document is baselined and distributed. Approval is logged in the Project Approval Register (IMT-PIG-021). |
| Change Control | Any change to an approved version requires a change request assessed through the project change control process. Minor editorial changes increment the minor version; changes affecting scope, cost, schedule, benefits or governance increment the major version and require re-approval. |
| Retention | Retained for the life of the project plus the organisational records-retention period, in the Project Information and Document Register. |

# 8.  Instructions for Completion

Complete every field. Where a field is not applicable, enter "N/A" and state the reason — never leave a field blank.

- List every recurring decision type the project will face. Work through the life cycle systematically rather than relying on recall — omitted decision types default to no one deciding.

- For each decision type, assign exactly one decider. Where two roles appear to share a decision, either split the decision into two distinct decisions or designate one as consulted.

- Record any monetary or materiality threshold that changes the decider, and state the escalation point above the threshold.

- Assign consultation rights sparingly. Every consultee adds elapsed time; consult those whose input changes the decision, and inform the rest.

- Assign veto rights only where a genuine control obligation exists — typically Legal, Compliance, Security, Safety or Finance. An unnecessary veto is a delivery bottleneck.

- Set a maximum response time for every decision type, and record the default position that applies if the deadline passes without a decision.

- Validate the matrix against the Authority Matrix (IMT-PIG-011). Any inconsistency between the two must be resolved before approval.

- Review the matrix with the sponsor and the steering committee, and obtain approval before delivery commences.

- Publish the matrix to the whole team and refer to it explicitly at the kick-off meeting.

- Record every significant decision in the decision log in Section E, including the decision-maker, the date, the options considered and the rationale.

NOTE A decision that is not made within the stated response time is itself a decision — usually the most expensive one available. Record the default position so that the consequence of inaction is visible in advance.

# 9.  Template — Project Decision-Making Matrix

Legend — P: Proposes · C: Consulted · D: Decides (one only per decision) · V: Veto right · I: Informed after the decision.

## Section A — Project Identification

| Project Name |  |
| --- | --- |
| Project Reference / ID |  |
| Project Manager |  |
| Project Sponsor |  |
| Governance Tier | ⟨ Tier 1 ¦ Tier 2 ¦ Tier 3 ⟩ |
| Delivery Approach | ⟨ Predictive ¦ Agile ¦ Hybrid ⟩ |
| Version and Date |  |
| Status | ⟨ Not Started ¦ In Progress ¦ Under Review ¦ Approved ¦ Rejected ¦ On Hold ¦ Completed ¦ Cancelled ⟩ |

## Section B — Decision Rights Matrix

| Ref | Decision Type | Team | PM | Product Owner | Sponsor | Steering Cttee | Portfolio Board | Threshold Applied | Max Response |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| D-01 | Approve the project charter |  | P |  | D | I | I | All | 5 wd |
| D-02 | Approve the project management plan baseline |  | P | C | D | I |  | All | 10 wd |
| D-03 | Approve a scope change within tolerance |  | P | C | D | I |  | Below threshold | 5 wd |
| D-04 | Approve a scope change above tolerance |  | P | C | C | D | I | Above threshold | 15 wd |
| D-05 | Approve expenditure within delegated authority |  | D |  | I |  |  | Below threshold | 3 wd |
| D-06 | Approve expenditure above delegated authority |  | P |  | D | I |  | Above threshold | 10 wd |
| D-07 | Release contingency reserve |  | P |  | D | I |  | Per framework | 5 wd |
| D-08 | Release management reserve |  | P |  | P | D | I | Per framework | 10 wd |
| D-09 | Accept a schedule variance within tolerance |  | D | C | I |  |  | Below tolerance | 3 wd |
| D-10 | Re-baseline the schedule |  | P | C | C | D | I | All | 10 wd |
| D-11 | Accept a risk above the project risk appetite |  | P |  | C | D | I | Per framework | 10 wd |
| D-12 | Approve a risk response requiring expenditure |  | P |  | D | I |  | Below threshold | 5 wd |
| D-13 | Accept a deliverable against acceptance criteria |  | P | C | D | I |  | All | 10 wd |
| D-14 | Approve a stage gate transition |  | P | C | C | D | I | All | 15 wd |
| D-15 | Approve supplier selection and award |  | P |  | C | D | I | Per procurement policy | 15 wd |
| D-16 | Issue an instruction or variation to a supplier |  | D |  | I |  |  | Below threshold | 3 wd |
| D-17 | Assign or release project team members |  | D | C | I |  |  | Within approved plan | 5 wd |
| D-18 | Approve technical or solution design | C | P | C | I |  |  | Design authority applies | 10 wd |
| D-19 | Prioritise the product backlog | C | C | D | I |  |  | All | 2 wd |
| D-20 | Determine iteration content and commitment | D | C | C |  |  |  | All | Same day |
| D-21 | Approve release to production | C | P | C | D | I |  | All | 5 wd |
| D-22 | Approve communication to external parties or regulators |  | P |  | C | D | I | All | 5 wd |
| D-23 | Suspend, restart or terminate the project |  | P |  | P | D | C | All | 15 wd |
| D-24 | Approve project closure and handover |  | P | C | D | C | I | All | 10 wd |
| D-25 | Approve a governance waiver or tailoring deviation |  | P |  | D | I | I | All | 10 wd |

NOTE The rows above are the recommended IMTITHAL baseline. Amend the allocation to reflect the approved Authority Matrix for the specific project, and delete any decision type that is genuinely not applicable rather than leaving it unassigned.

## Section C — Veto Rights and Mandatory Consultations

| Decision Ref | Function Holding the Right | Right Held (Veto / Mandatory Consultation) | Basis of the Right | Response Time Obligation |
| --- | --- | --- | --- | --- |
| D-21 | Information Security | Veto | Corporate security policy — production release control | 3 working days |

## Section D — Default Positions and Escalation on Non-Decision

| Decision Ref | Default if No Decision Within the Response Time | Escalation Route | Escalation Trigger Point | Owner of the Escalation |
| --- | --- | --- | --- | --- |
| D-05 | Expenditure is not committed; activity is held | PM → Sponsor | Response time exceeded by 2 working days | Project Manager |

## Section E — Project Decision Log

| Ref | Date | Decision Required | Options Considered | Decision Taken | Rationale | Decision-Maker | Type Ref | Impact | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| DL-01 | DD-MMM | Select the integration approach | Direct API / middleware / batch | Middleware | Lowest change impact on legacy platform | Sponsor | D-18 | Cost +40k | Closed |

## Section F — Decision Performance Monitoring

| Measure | Target | Current Period | Trend |
| --- | --- | --- | --- |
| Decisions taken within the stated response time | ≥ 90% |  |  |
| Decisions escalated above the assigned level | ≤ 10% |  |  |
| Decisions reopened after being taken | ≤ 5% |  |  |
| Average elapsed time from request to decision | ≤ 5 working days |  |  |
| Open decisions past their response deadline | 0 |  |  |

# 10.  Approval and Authorisation

By signing below, each approver confirms that the content of this document has been reviewed, is accurate to the best of their knowledge, and is authorised for use within the project.

| Approval Role | Name | Position / Title | Signature | Date |
| --- | --- | --- | --- | --- |
| Prepared by (Project Manager) |  |  |  |  |
| Reviewed by (PMO) |  |  |  |  |
| Approved by (Project Sponsor) |  |  |  |  |

# 11.  Revision History

| Version | Date | Description of Change | Prepared / Revised By | Approved By |
| --- | --- | --- | --- | --- |
| 0.1 | DD-MMM-YYYY | Initial draft prepared for review | Project Manager | — |
| 0.9 | DD-MMM-YYYY | Reviewed by PMO; comments incorporated | PMO Analyst | — |
| 1.0 | 01-Sep-2026 | First approved and issued baseline | Project Manager | Project Sponsor; endorsed by the PMO for consistency with the Governance Framework |

NOTE Rows shown in shaded italics are illustrative examples of how the revision history is completed. Replace them with the actual revision record.

# 12.  Notice and Disclaimer

PMI®, PMBOK®, PMP®, PMI-ACP® and PfMP® are registered marks of the Project Management Institute, Inc. This document is an original work product of IMTITHAL, developed in alignment with the principles, performance domains and focus areas described in the PMBOK® Guide – Eighth Edition. It is not issued, certified, endorsed or approved by PMI, and it does not reproduce PMI copyrighted text or proprietary PMI templates. Organisations remain responsible for tailoring this document to their own governance, contractual and regulatory obligations.