IMTITHAL PROJECT MANAGEMENT SYSTEM PMBOK® Guide – Eighth Edition Aligned

TOOLKIT 01  |  PROJECT INITIATION & GOVERNANCE

PROJECT AUTHORITY MATRIX

Delegated financial, contractual and management authority by role

Document Reference:  IMT-PIG-011

| DOCUMENT CONTROL |  |  |  |
| --- | --- | --- | --- |
| File Name | IMT-PIG-011_Project_Authority_Matrix_v1.0.docx | Version | 1.0 |
| Document Owner | Project Management Office (PMO) | Document Status | Approved – Issued for Use |
| Approval Authority | Project Sponsor and Finance (for financial authority limits); Portfolio Board where limits exceed sponsor delegation | Classification | Internal – Controlled Document |
| Effective Date | 01-Sep-2026 | Revision Date | 01-Sep-2026 |
| Next Review Date | 01-Sep-2027 | Review Frequency | At every stage gate, on any change of role holder, and on any change to the approved budget |

IMTITHAL Project Management System · Toolkit 01: Project Initiation & Governance This document is an original IMTITHAL work product developed in alignment with the concepts and practices of the PMBOK® Guide – Eighth Edition. PMI, PMBOK, PMP and PMI-ACP are marks of the Project Management Institute, Inc. IMTITHAL is not affiliated with, endorsed by, certified by, or approved by PMI. No PMI copyrighted text or proprietary PMI template is reproduced herein.

# 1.  Purpose

The Authority Matrix records the limits of delegated authority held by each project role — financial commitment, contractual instruction, resource assignment, change approval, risk acceptance, acceptance of deliverables and communication. It states the value or materiality threshold attaching to each authority, the escalation point above that threshold, and the conditions and evidence required for the authority to be validly exercised. It is the control that keeps project decision-making inside the organisation's delegation of authority policy.

- States precisely what each role may commit, approve, instruct or accept, and up to what limit.

- Aligns project authority with corporate delegation of authority and financial regulations.

- Prevents unauthorised commitment, the most common source of project audit findings.

- Provides the reference used when validating approvals in the Project Approval Register.

# 2.  When to Use

- During initiation, before any expenditure or contractual commitment is made.

- Whenever a role holder changes, or a delegation is temporarily transferred to a deputy.

- When the approved budget or the project tier changes, since thresholds are usually value-based.

- During procurement, contract award and variation approval.

- During audit, assurance review and financial verification of project transactions.

# 3.  Responsibility and Approval

| Governance Role | Assignment | Description of Involvement |
| --- | --- | --- |
| Responsible (prepares) | Project Manager, in consultation with the Finance Business Partner and the PMO | Prepares, populates and maintains the document; ensures accuracy and completeness of all fields. |
| Accountable (owns) | Project Sponsor | Single point of accountability for the quality, currency and control of the document. |
| Consulted | PMO, Finance, Risk, Quality, Legal/Contracts, business owners and technical disciplines as applicable | Provides subject-matter input before submission for approval. |
| Informed | Project team, affected business units, supporting functions, key external stakeholders | Receives the approved document through the controlled distribution list. |
| Approves | Project Sponsor and Finance (for financial authority limits); Portfolio Board where limits exceed sponsor delegation | Formally authorises the document; approval is recorded in the Project Approval Register. |

# 4.  Required Inputs

- Organisational delegation of authority policy and financial regulations.

- Approved Project Charter, including the project manager authority section.

- Project Governance Framework (IMT-PIG-008) authority thresholds.

- Approved project budget, contingency and management reserve amounts.

- Procurement policy, contract templates and signing authority rules.

- Named role holders from the Governance Structure (IMT-PIG-009).

# 5.  Required Outputs

- An approved matrix of delegated authority limits by role.

- Defined escalation points for every authority above its threshold.

- Documented deputisation and temporary delegation arrangements.

- The control basis for validating approvals and for audit evidence.

# 6.  PMBOK® Guide – Eighth Edition Alignment

This document has been designed in alignment with the following elements of the PMBOK® Guide – Eighth Edition. The alignment statement is provided for conceptual traceability only.

| Focus Area | Initiating and Planning; applied throughout delivery |
| --- | --- |
| Performance Domains | Governance and Finance (primary); Resources, Risk, Scope (supporting) |
| Guiding Principles | Be an accountable leader · Build an empowered culture · Embed quality into processes |
| Tailoring Consideration | Thresholds are expressed either as absolute amounts or as a percentage of the approved budget. Percentage-based thresholds scale automatically across projects and are recommended for portfolios with a wide range of project values. |

# 7.  Review Frequency and Approval Requirements

| Review Frequency | At every stage gate, on any change of role holder, and on any change to the approved budget |
| --- | --- |
| Review Triggers | Change of sponsor or governance structure; change of delivery approach; stage-gate decision; material change to scope, cost, schedule, benefits or risk exposure; audit or assurance finding; organisational restructuring. |
| Approval Requirements | Approved by the Project Sponsor and validated by Finance. Limits that exceed the sponsor's own delegated authority require Portfolio Board approval. No authority may be exercised before the matrix is approved. |
| Change Control | Any change to an approved version requires a change request assessed through the project change control process. Minor editorial changes increment the minor version; changes affecting scope, cost, schedule, benefits or governance increment the major version and require re-approval. |
| Retention | Retained for the life of the project plus the organisational records-retention period, in the Project Information and Document Register. |

# 8.  Instructions for Completion

Complete every field. Where a field is not applicable, enter "N/A" and state the reason — never leave a field blank.

- Obtain the current organisational delegation of authority policy before completing the matrix. Project limits must sit within corporate limits, never above them.

- Complete Section B for each named role holder. Record the role, the individual and the effective date of the delegation.

- For each authority type in Section C, record the limit, the unit in which it is expressed, the conditions of exercise and the escalation point above the limit.

- Express financial limits per transaction and, where applicable, per cumulative period, to prevent a limit being circumvented by splitting a commitment into smaller parts.

- Record the evidence required for each authority to be validly exercised — approved requisition, signed change request, minuted steering committee decision.

- Complete Section D for non-financial authority: resource assignment, contractual instruction, acceptance of deliverables, risk acceptance and external communication.

- Record temporary delegations in Section E, with the start and end date and the extent and limits of the delegated authority.

- Record in Section F any authority explicitly reserved to a body and not delegated at all.

- Obtain sponsor and Finance approval, then publish the matrix and provide it to Finance and Procurement so that transactions can be validated at source.

- Verify compliance periodically by sampling approvals in the Project Approval Register against this matrix, and report exceptions through governance.

NOTE Splitting a commitment to stay below a threshold is a control breach even where each individual transaction is within limits. State the anti-splitting rule explicitly in Section C and apply it in transaction validation.

# 9.  Template — Project Authority Matrix

## Section A — Project and Budget Identification

| Project Name |  |
| --- | --- |
| Project Reference / ID |  |
| Approved Budget | ⟨ currency and amount ⟩ |
| Contingency Reserve | ⟨ amount ⟩ |
| Management Reserve | ⟨ amount ⟩ |
| Currency |  |
| Governance Tier | ⟨ Tier 1 ¦ Tier 2 ¦ Tier 3 ⟩ |
| Corporate DoA Policy Reference | ⟨ policy number and version ⟩ |
| Matrix Effective Date |  |
| Status | ⟨ Not Started ¦ In Progress ¦ Under Review ¦ Approved ¦ Rejected ¦ On Hold ¦ Completed ¦ Cancelled ⟩ |

## Section B — Named Role Holders and Delegations

| Role | Name | Position | Delegation Effective From | Delegation Expires | Delegating Authority |
| --- | --- | --- | --- | --- | --- |
| Project Manager | Name | Senior Project Manager | DD-MMM-YYYY | Project closure | Project Sponsor |

## Section C — Financial Authority Limits

| Financial Authority | Team Lead | Project Manager | Sponsor | Steering Cttee | Portfolio Board | Evidence Required |
| --- | --- | --- | --- | --- | --- | --- |
| Commit expenditure per transaction |  |  |  |  |  | Approved requisition |
| Commit expenditure per month (cumulative) |  |  |  |  |  | Monthly commitment report |
| Approve invoice for payment |  |  |  |  |  | Goods/services receipt |
| Approve a budget virement between cost lines |  |  |  |  |  | Virement request |
| Draw down contingency reserve |  |  |  |  |  | Risk register entry and change request |
| Draw down management reserve |  |  |  |  |  | Steering committee minute |
| Approve a cost increase to the approved envelope |  |  |  |  |  | Revised business case |
| Award a contract |  |  |  |  |  | Evaluation report and recommendation |
| Approve a contract variation |  |  |  |  |  | Signed variation instruction |
| Approve a write-off or de-scoping with cost impact |  |  |  |  |  | Approved change request |

| Threshold Basis | ⟨ absolute amount ¦ percentage of approved budget ⟩ |
| --- | --- |
| Anti-Splitting Rule | ⟨ commitments to a single supplier or for a single purpose within a defined period are aggregated for threshold purposes ⟩ |
| Currency Conversion Rule | ⟨ rate source and date applied for foreign-currency commitments ⟩ |
| Emergency Authority Provision | ⟨ who may act outside limits in an emergency, and the ratification requirement ⟩ |

## Section D — Non-Financial Authority

| Authority | Team Lead | Project Manager | Sponsor | Steering Cttee | Conditions of Exercise |
| --- | --- | --- | --- | --- | --- |
| Assign project team members to work |  |  |  |  |  |
| Release team members from the project |  |  |  |  |  |
| Engage external contractors or consultants |  |  |  |  |  |
| Approve a change to scope |  |  |  |  |  |
| Approve a change to the schedule baseline |  |  |  |  |  |
| Accept a deliverable against its acceptance criteria |  |  |  |  |  |
| Accept a residual risk |  |  |  |  |  |
| Approve a deviation from a technical standard |  |  |  |  |  |
| Approve a governance or methodology waiver |  |  |  |  |  |
| Instruct a supplier |  |  |  |  |  |
| Communicate externally on behalf of the project |  |  |  |  |  |
| Engage with a regulator or auditor |  |  |  |  |  |
| Approve release of information classified as confidential |  |  |  |  |  |
| Suspend project work |  |  |  |  |  |

## Section E — Temporary Delegations and Deputisation

| Ref | Authority Delegated | From (Role Holder) | To (Deputy) | Effective From | Expires | Limits Applied | Approved By |
| --- | --- | --- | --- | --- | --- | --- | --- |
| TD-01 | Expenditure up to 50% of PM limit | Project Manager | Delivery Lead | DD-MMM | DD-MMM | No contract award | Sponsor |

## Section F — Authority Reserved and Not Delegated

| Reserved Authority | Reserved To | Reason for Reservation | Policy Reference |
| --- | --- | --- | --- |
| Approval of any increase to the total approved investment | Portfolio Board | Corporate delegation of authority policy limit | DoA Policy §4.2 |

## Section G — Authority Compliance Monitoring

| Review Date | Transactions Sampled | Compliant | Exceptions Identified | Action Taken | Reviewed By |
| --- | --- | --- | --- | --- | --- |

# 10.  Approval and Authorisation

By signing below, each approver confirms that the content of this document has been reviewed, is accurate to the best of their knowledge, and is authorised for use within the project.

| Approval Role | Name | Position / Title | Signature | Date |
| --- | --- | --- | --- | --- |
| Prepared by (Project Manager) |  |  |  |  |
| Validated by (Finance Business Partner) |  |  |  |  |
| Reviewed by (PMO) |  |  |  |  |
| Approved by (Project Sponsor) |  |  |  |  |

# 11.  Revision History

| Version | Date | Description of Change | Prepared / Revised By | Approved By |
| --- | --- | --- | --- | --- |
| 0.1 | DD-MMM-YYYY | Initial draft prepared for review | Project Manager | — |
| 0.9 | DD-MMM-YYYY | Reviewed by PMO; comments incorporated | PMO Analyst | — |
| 1.0 | 01-Sep-2026 | First approved and issued baseline | Project Manager | Project Sponsor and Finance (for financial authority limits); Portfolio Board where limits exceed sponsor delegation |

NOTE Rows shown in shaded italics are illustrative examples of how the revision history is completed. Replace them with the actual revision record.

# 12.  Notice and Disclaimer

PMI®, PMBOK®, PMP®, PMI-ACP® and PfMP® are registered marks of the Project Management Institute, Inc. This document is an original work product of IMTITHAL, developed in alignment with the principles, performance domains and focus areas described in the PMBOK® Guide – Eighth Edition. It is not issued, certified, endorsed or approved by PMI, and it does not reproduce PMI copyrighted text or proprietary PMI templates. Organisations remain responsible for tailoring this document to their own governance, contractual and regulatory obligations.