IMTITHAL PROJECT MANAGEMENT SYSTEM PMBOK® Guide – Eighth Edition Aligned

TOOLKIT 01  |  PROJECT INITIATION & GOVERNANCE

RACI MATRIX

Responsibility assignment across project activities and deliverables

Document Reference:  IMT-PIG-013

| DOCUMENT CONTROL |  |  |  |
| --- | --- | --- | --- |
| File Name | IMT-PIG-013_RACI_Matrix_v1.0.docx | Version | 1.0 |
| Document Owner | Project Management Office (PMO) | Document Status | Approved – Issued for Use |
| Approval Authority | Project Sponsor; endorsed by each function lead named in the matrix | Classification | Internal – Controlled Document |
| Effective Date | 01-Sep-2026 | Revision Date | 01-Sep-2026 |
| Next Review Date | 01-Sep-2027 | Review Frequency | At every stage gate, and whenever roles, scope or supplier arrangements change |

IMTITHAL Project Management System · Toolkit 01: Project Initiation & Governance This document is an original IMTITHAL work product developed in alignment with the concepts and practices of the PMBOK® Guide – Eighth Edition. PMI, PMBOK, PMP and PMI-ACP are marks of the Project Management Institute, Inc. IMTITHAL is not affiliated with, endorsed by, certified by, or approved by PMI. No PMI copyrighted text or proprietary PMI template is reproduced herein.

# 1.  Purpose

The RACI Matrix assigns, for every significant project activity and deliverable, who is Responsible for performing the work, who is Accountable for the outcome, who must be Consulted before it is completed, and who must be Informed once it is done. Its value lies in enforcing a single accountable role per activity and in exposing both unallocated work and over-consultation before they cause delay. It is the operational companion to the Roles and Responsibilities Matrix.

- Enforces exactly one accountable role for every activity and deliverable.

- Reveals activities with no responsible party and roles that are overloaded.

- Reduces elapsed time by limiting consultation to those whose input changes the outcome.

- Provides the operational reference used in day-to-day delivery and in handover.

# 2.  When to Use

- During planning, once the deliverables and the roles are both defined.

- When work is handed between teams, functions or suppliers.

- When an activity is repeatedly delayed, duplicated or missed.

- When new roles or new work packages are added during delivery.

- At each stage gate, since responsibility patterns change between phases.

# 3.  Responsibility and Approval

| Governance Role | Assignment | Description of Involvement |
| --- | --- | --- |
| Responsible (prepares) | Project Manager, in workshop with the team and function leads | Prepares, populates and maintains the document; ensures accuracy and completeness of all fields. |
| Accountable (owns) | Project Manager | Single point of accountability for the quality, currency and control of the document. |
| Consulted | PMO, Finance, Risk, Quality, Legal/Contracts, business owners and technical disciplines as applicable | Provides subject-matter input before submission for approval. |
| Informed | Project team, affected business units, supporting functions, key external stakeholders | Receives the approved document through the controlled distribution list. |
| Approves | Project Sponsor; endorsed by each function lead named in the matrix | Formally authorises the document; approval is recorded in the Project Approval Register. |

# 4.  Required Inputs

- Roles and Responsibilities Matrix (IMT-PIG-012) and the Organisation Chart (IMT-PIG-014).

- Scope structure, deliverable list and work package breakdown.

- Project schedule and the phase or iteration structure.

- Decision-Making Matrix (IMT-PIG-010) and Authority Matrix (IMT-PIG-011).

- Governance and reporting obligations requiring named responsibility.

# 5.  Required Outputs

- An approved responsibility assignment for every activity and deliverable.

- Identified unallocated activities and overloaded roles, with resolution actions.

- An agreed basis for performance expectations and for handover between phases.

- Input to the communications plan through the consulted and informed assignments.

# 6.  PMBOK® Guide – Eighth Edition Alignment

This document has been designed in alignment with the following elements of the PMBOK® Guide – Eighth Edition. The alignment statement is provided for conceptual traceability only.

| Focus Area | Planning; applied through Executing and Monitoring and Controlling |
| --- | --- |
| Performance Domains | Resources (primary); Governance, Scope, Stakeholders (supporting) |
| Guiding Principles | Be an accountable leader · Build an empowered culture · Embed quality into processes |
| Tailoring Consideration | Agile teams may apply RACI at feature or epic level rather than task level, preserving team self-organisation within the increment. Where governance requires it, the extended RACI-VS variant adds Verifier and Signatory. Do not apply RACI below the level at which the team is genuinely empowered to organise its own work. |

# 7.  Review Frequency and Approval Requirements

| Review Frequency | At every stage gate, and whenever roles, scope or supplier arrangements change |
| --- | --- |
| Review Triggers | Change of sponsor or governance structure; change of delivery approach; stage-gate decision; material change to scope, cost, schedule, benefits or risk exposure; audit or assurance finding; organisational restructuring. |
| Approval Requirements | Formal written approval by the stated Approval Authority before the document is baselined and distributed. Approval is logged in the Project Approval Register (IMT-PIG-021). |
| Change Control | Any change to an approved version requires a change request assessed through the project change control process. Minor editorial changes increment the minor version; changes affecting scope, cost, schedule, benefits or governance increment the major version and require re-approval. |
| Retention | Retained for the life of the project plus the organisational records-retention period, in the Project Information and Document Register. |

# 8.  Instructions for Completion

Complete every field. Where a field is not applicable, enter "N/A" and state the reason — never leave a field blank.

- Build the matrix in a facilitated workshop with the people named in it. A RACI written in isolation is not a commitment.

- List activities and deliverables down the rows and roles across the columns. Use the same activity references as the schedule and scope structure so the matrix remains traceable.

- Assign exactly one A (Accountable) to every row. Two accountable roles means no accountable role.

- Assign at least one R (Responsible) to every row. A row with an A but no R indicates work that has been approved but not resourced.

- Limit C (Consulted) assignments to those whose input will actually change the outcome. Each consultation adds elapsed time and should be justified.

- Use I (Informed) for those who need the result but not a voice in producing it. Route the informed assignments into the communications plan.

- Run the analysis in Section D. Check every row for a single A and at least one R, and every column for an overloaded role. Resolve every exception before approval.

- Where a supplier or external party holds an assignment, confirm that the contract actually obliges them to perform it. An assignment without a contractual basis is unenforceable.

- Obtain endorsement from each function lead and approval from the sponsor, then publish and use the matrix operationally rather than filing it.

- Update at each gate and whenever roles change; issue a new version and communicate the differences rather than silently amending.

NOTE Legend — R: Responsible (performs the work) · A: Accountable (answerable for the outcome; exactly one per row) · C: Consulted (two-way dialogue before completion) · I: Informed (one-way notification after completion).

# 9.  Template — RACI Matrix

## Section A — Project Identification

| Project Name |  |
| --- | --- |
| Project Reference / ID |  |
| Project Manager |  |
| Project Sponsor |  |
| Delivery Approach | ⟨ Predictive ¦ Agile ¦ Hybrid ⟩ |
| Matrix Level Applied | ⟨ Deliverable ¦ Work package ¦ Activity ¦ Feature ⟩ |
| Version and Date |  |
| Status | ⟨ Not Started ¦ In Progress ¦ Under Review ¦ Approved ¦ Rejected ¦ On Hold ¦ Completed ¦ Cancelled ⟩ |

## Section B — Role Key

| Column Code | Role Title | Role Holder | Function / Organisation |
| --- | --- | --- | --- |
| SP | Project Sponsor | Name | Operations |

## Section C — Responsibility Assignment Matrix

Enter R, A, C or I in each cell. Leave a cell blank where the role has no involvement.

| Ref | Activity / Deliverable | SP | BO | PM | PMO | PO | BA | AR | DT | QA | FIN |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A-01 | Develop and submit the project proposal | A | R | C | C |  |  |  |  |  | C |
| A-02 | Develop the business case | A | R | C | C |  | C |  |  |  | R |
| A-03 | Develop the project charter | A | C | R | C |  |  |  |  |  | I |
| A-04 | Define objectives and success criteria | A | R | R | C | C | C |  |  | C | I |
| A-05 | Identify and quantify benefits | A | R | C | C |  | C |  |  |  | R |
| A-06 | Establish the governance structure | A | C | R | C |  |  |  | I |  | I |
| A-07 | Select the delivery approach and tailor the method | A | C | R | C | C | C | C | C | C |  |
| A-08 | Elicit and analyse requirements | I | A | C |  | R | R | C | C | C |  |
| A-09 | Develop the scope structure | I | C | A | C | C | R | C | R |  |  |
| A-10 | Develop the schedule and baseline it | A | C | R | C | C | C | C | C |  | C |
| A-11 | Estimate costs and develop the budget | A | C | R | C |  | C | C | C |  | R |
| A-12 | Identify, analyse and respond to risks | A | C | R | C | C | C | C | C | C | C |
| A-13 | Produce the solution design | I | C | A |  | C | C | R | C | C |  |
| A-14 | Build and configure the solution | I | I | A |  | C | C | C | R | C |  |
| A-15 | Test and verify the solution | I | C | A |  | C | C | C | R | R |  |
| A-16 | Manage change requests | A | C | R | C | C | C | C | I |  | C |
| A-17 | Report project status and performance | I | I | A | R | C |  |  | I |  | C |
| A-18 | Manage suppliers and contracts | A | I | R | C |  |  |  | I |  | C |
| A-19 | Prepare operational readiness and transition | A | R | C | C | C | C | C | C | R |  |
| A-20 | Accept deliverables | A | R | C | I | C | C | C | I | R |  |
| A-21 | Deploy to production and go live | A | C | R | I | C |  | C | R | C |  |
| A-22 | Track and report benefit realisation | A | R | C | C |  |  |  |  |  | C |
| A-23 | Capture and publish lessons learned | I | C | A | R | C | C | C | C | C |  |
| A-24 | Close the project and archive records | A | C | R | R | I | I | I | I | I | C |

NOTE Column key used above — SP: Sponsor · BO: Business Owner · PM: Project Manager · PMO: PMO Representative · PO: Product Owner · BA: Business Analyst · AR: Architect · DT: Delivery Team · QA: Quality / Test · FIN: Finance. Replace the columns and the assignments with those applicable to your project.

## Section D — Matrix Analysis and Exceptions

| Check | Rule | Exceptions Identified | Resolution and Owner |
| --- | --- | --- | --- |
| Single accountability | Exactly one A per row |  |  |
| Work is resourced | At least one R per row |  |  |
| No unallocated activity | No row entirely blank |  |  |
| Consultation is proportionate | No row with more than four C |  |  |
| Role load is sustainable | No role with an excessive count of R |  |  |
| Accountability is concentrated appropriately | A held only by roles with matching authority |  |  |
| External assignments are enforceable | Supplier R or A supported by a contract clause |  |  |

## Section E — Role Loading Summary

| Role | Count of A | Count of R | Count of C | Count of I | Assessment | Action Required |
| --- | --- | --- | --- | --- | --- | --- |

## Section F — Change Log for Responsibility Assignments

| Date | Activity Ref | Change Made | Reason | Requested By | Approved By |
| --- | --- | --- | --- | --- | --- |

# 10.  Approval and Authorisation

By signing below, each approver confirms that the content of this document has been reviewed, is accurate to the best of their knowledge, and is authorised for use within the project.

| Approval Role | Name | Position / Title | Signature | Date |
| --- | --- | --- | --- | --- |
| Prepared by (Project Manager) |  |  |  |  |
| Endorsed by (Function Leads) |  |  |  |  |
| Reviewed by (PMO) |  |  |  |  |
| Approved by (Project Sponsor) |  |  |  |  |

# 11.  Revision History

| Version | Date | Description of Change | Prepared / Revised By | Approved By |
| --- | --- | --- | --- | --- |
| 0.1 | DD-MMM-YYYY | Initial draft prepared for review | Project Manager | — |
| 0.9 | DD-MMM-YYYY | Reviewed by PMO; comments incorporated | PMO Analyst | — |
| 1.0 | 01-Sep-2026 | First approved and issued baseline | Project Manager | Project Sponsor; endorsed by each function lead named in the matrix |

NOTE Rows shown in shaded italics are illustrative examples of how the revision history is completed. Replace them with the actual revision record.

# 12.  Notice and Disclaimer

PMI®, PMBOK®, PMP®, PMI-ACP® and PfMP® are registered marks of the Project Management Institute, Inc. This document is an original work product of IMTITHAL, developed in alignment with the principles, performance domains and focus areas described in the PMBOK® Guide – Eighth Edition. It is not issued, certified, endorsed or approved by PMI, and it does not reproduce PMI copyrighted text or proprietary PMI templates. Organisations remain responsible for tailoring this document to their own governance, contractual and regulatory obligations.