IMTITHAL PROJECT MANAGEMENT SYSTEM PMBOK® Guide – Eighth Edition Aligned

TOOLKIT 01  |  PROJECT INITIATION & GOVERNANCE

PREDICTIVE, AGILE AND HYBRID SUITABILITY ASSESSMENT

Structured scored assessment of delivery approach suitability

Document Reference:  IMT-PIG-016

| DOCUMENT CONTROL |  |  |  |
| --- | --- | --- | --- |
| File Name | IMT-PIG-016_Predictive_Agile_and_Hybrid_Suitability_Assessment_v1.0.docx | Version | 1.0 |
| Document Owner | Project Management Office (PMO) | Document Status | Approved – Issued for Use |
| Approval Authority | PMO Manager (methodological validation) and Project Sponsor (acceptance of the resulting approach) | Classification | Internal – Controlled Document |
| Effective Date | 01-Sep-2026 | Revision Date | 01-Sep-2026 |
| Next Review Date | 01-Sep-2027 | Review Frequency | At each stage gate, and whenever a driving characteristic changes materially |

IMTITHAL Project Management System · Toolkit 01: Project Initiation & Governance This document is an original IMTITHAL work product developed in alignment with the concepts and practices of the PMBOK® Guide – Eighth Edition. PMI, PMBOK, PMP and PMI-ACP are marks of the Project Management Institute, Inc. IMTITHAL is not affiliated with, endorsed by, certified by, or approved by PMI. No PMI copyrighted text or proprietary PMI template is reproduced herein.

# 1.  Purpose

This assessment provides a structured, scored evaluation of which delivery approach best fits a specific project. It examines the project across four dimensions — product and requirement characteristics, organisational and team characteristics, stakeholder and customer characteristics, and governance and constraint characteristics — and converts qualitative judgement into a comparable score that indicates a predictive, agile or hybrid approach. It exists to replace approach selection by habit or preference with approach selection by evidence.

- Converts approach selection from an opinion into a scored, comparable assessment.

- Exposes the specific factors that make an approach suitable or unsuitable.

- Identifies the preconditions that must be created if a preferred approach is to succeed.

- Provides auditable evidence supporting the approach recorded in the Charter.

# 2.  When to Use

- During initiation, before the approach is selected and before planning begins.

- When a phase of the project may warrant a different approach from the preceding phase.

- When requirement volatility, team structure or stakeholder availability proves different from what was assumed.

- At each stage gate, as a short re-test of continued suitability.

- When a supplier proposes a delivery model different from the one assumed.

# 3.  Responsibility and Approval

| Governance Role | Assignment | Description of Involvement |
| --- | --- | --- |
| Responsible (prepares) | Project Manager, scored jointly with the delivery team, business owner and PMO | Prepares, populates and maintains the document; ensures accuracy and completeness of all fields. |
| Accountable (owns) | Project Manager | Single point of accountability for the quality, currency and control of the document. |
| Consulted | PMO, Finance, Risk, Quality, Legal/Contracts, business owners and technical disciplines as applicable | Provides subject-matter input before submission for approval. |
| Informed | Project team, affected business units, supporting functions, key external stakeholders | Receives the approved document through the controlled distribution list. |
| Approves | PMO Manager (methodological validation) and Project Sponsor (acceptance of the resulting approach) | Formally authorises the document; approval is recorded in the Project Approval Register. |

# 4.  Required Inputs

- Project Charter and Business Case, providing objectives, constraints and drivers.

- Preliminary requirement analysis and an assessment of requirement stability.

- Team composition, availability, location and delivery experience.

- Stakeholder availability and willingness to engage iteratively.

- Governance, regulatory, audit and contractual obligations.

- Organisational delivery maturity assessment and tooling availability.

# 5.  Required Outputs

- A completed and scored suitability assessment with a dimension-level breakdown.

- An indicated approach with the factors that most strongly drive the indication.

- A list of preconditions required for the indicated approach to succeed.

- Documented input to the Approach Selection Form (IMT-PIG-015) and the Tailoring Assessment (IMT-PIG-017).

# 6.  PMBOK® Guide – Eighth Edition Alignment

This document has been designed in alignment with the following elements of the PMBOK® Guide – Eighth Edition. The alignment statement is provided for conceptual traceability only.

| Focus Area | Initiating |
| --- | --- |
| Performance Domains | Governance and Scope (primary); Schedule, Resources, Stakeholders, Risk (supporting) |
| Guiding Principles | Adopt a holistic view · Focus on value · Build an empowered culture · Be an accountable leader |
| Tailoring Consideration | Adjust the criterion weightings to reflect organisational context — regulated environments typically increase the weighting of governance and evidence criteria. Record any weighting change and its rationale before scoring, never after. |

# 7.  Review Frequency and Approval Requirements

| Review Frequency | At each stage gate, and whenever a driving characteristic changes materially |
| --- | --- |
| Review Triggers | Change of sponsor or governance structure; change of delivery approach; stage-gate decision; material change to scope, cost, schedule, benefits or risk exposure; audit or assurance finding; organisational restructuring. |
| Approval Requirements | Validated by the PMO for methodological consistency and accepted by the Project Sponsor. The assessment result is advisory; where the selected approach differs from the indication, the override must be justified in IMT-PIG-015 Section C4. |
| Change Control | Any change to an approved version requires a change request assessed through the project change control process. Minor editorial changes increment the minor version; changes affecting scope, cost, schedule, benefits or governance increment the major version and require re-approval. |
| Retention | Retained for the life of the project plus the organisational records-retention period, in the Project Information and Document Register. |

# 8.  Instructions for Completion

Complete every field. Where a field is not applicable, enter "N/A" and state the reason — never leave a field blank.

- Agree and record the criterion weightings before scoring begins. Weighting after seeing the scores invalidates the assessment.

- Score collaboratively in a facilitated session with the project manager, the delivery team, the business owner and a PMO representative. A single-person assessment reflects a single perspective.

- Score each criterion from 1 to 5 using the descriptors provided. Where the group cannot agree, record the range and the reason for disagreement — divergence is itself useful information.

- Calculate the dimension scores and the total score in Section F. A higher score indicates greater suitability for adaptive delivery; a lower score indicates greater suitability for predictive delivery.

- Read the indication in Section G, then examine the individual criteria scoring at the extremes. A criterion scoring 1 or 5 usually determines the practical approach regardless of the total.

- Complete Section H. Where the indicated approach requires preconditions that do not currently exist, record them as actions with owners and dates, or accept a different approach.

- Where the assessment indicates hybrid, use Section I to identify which components are suited to which approach rather than applying a uniform compromise across the whole project.

- Record the conclusion and pass it to the Approach Selection Form (IMT-PIG-015) for the formal decision.

- Retain the completed assessment as evidence supporting the approach recorded in the Charter and re-test it at each gate.

NOTE The total score indicates direction, not destiny. A single criterion scoring at the extreme — for example a regulator requiring a fixed, evidenced baseline, or a product owner who cannot be made available — will in practice determine the approach whatever the total score suggests.

# 9.  Template — Predictive, Agile and Hybrid Suitability Assessment

Scoring scale: 1 = strongly favours predictive · 2 = favours predictive · 3 = neutral or mixed · 4 = favours adaptive · 5 = strongly favours adaptive.

## Section A — Assessment Identification

| Project Name |  |
| --- | --- |
| Project Reference / ID |  |
| Assessment Date |  |
| Facilitated By |  |
| Participants | ⟨ names and roles of all who scored ⟩ |
| Assessment Trigger | ⟨ Initiation ¦ Gate review ¦ Change in characteristics ⟩ |
| Version |  |
| Status | ⟨ Not Started ¦ In Progress ¦ Under Review ¦ Approved ¦ Rejected ¦ On Hold ¦ Completed ¦ Cancelled ⟩ |

## Section B — Dimension 1: Product and Requirement Characteristics

| Ref | Criterion | Score 1–2 Indicates | Score 4–5 Indicates | Weight | Score | Weighted |
| --- | --- | --- | --- | --- | --- | --- |
| P1 | Stability of requirements | Requirements fixed and well understood | Requirements expected to evolve substantially | 5 |  |  |
| P2 | Clarity of the end product | End state fully definable now | End state emerges through delivery | 5 |  |  |
| P3 | Technical novelty | Proven technology and known patterns | Novel technology, significant unknowns | 4 |  |  |
| P4 | Divisibility into increments | Value only on full completion | Usable value delivered incrementally | 5 |  |  |
| P5 | Cost of change late in delivery | Very high — physical or contractual | Low — change is inexpensive | 4 |  |  |
| P6 | Ability to test and learn early | Testing possible only at the end | Continuous testing and feedback possible | 4 |  |  |
| P7 | Interdependence with fixed external milestones | Tightly coupled to fixed external dates | Largely independent | 3 |  |  |

## Section C — Dimension 2: Organisation and Team Characteristics

| Ref | Criterion | Score 1–2 Indicates | Score 4–5 Indicates | Weight | Score | Weighted |
| --- | --- | --- | --- | --- | --- | --- |
| O1 | Team dedication | Part-time, shared across initiatives | Dedicated, stable team | 5 |  |  |
| O2 | Team co-location or connectedness | Dispersed with limited overlap | Co-located or strongly connected | 3 |  |  |
| O3 | Team experience with adaptive delivery | None | Experienced and proficient | 4 |  |  |
| O4 | Team empowerment to decide | Decisions escalated routinely | Team authorised to decide within scope | 4 |  |  |
| O5 | Organisational delivery maturity | Low; process compliance driven | High; outcome driven | 3 |  |  |
| O6 | Cross-functional capability within the team | Specialist silos with handoffs | Cross-functional and self-sufficient | 4 |  |  |
| O7 | Tooling to support the approach | Absent | Available and in use | 2 |  |  |

## Section D — Dimension 3: Stakeholder and Customer Characteristics

| Ref | Criterion | Score 1–2 Indicates | Score 4–5 Indicates | Weight | Score | Weighted |
| --- | --- | --- | --- | --- | --- | --- |
| S1 | Availability of an empowered product owner | Not available | Dedicated and empowered | 5 |  |  |
| S2 | Customer willingness to engage continuously | Engages only at milestones | Engages every iteration | 4 |  |  |
| S3 | Stakeholder tolerance of emergent scope | Requires fixed scope commitment | Comfortable with evolving scope | 4 |  |  |
| S4 | Speed of stakeholder decision-making | Slow, committee-based | Fast, delegated | 3 |  |  |
| S5 | Number of stakeholder groups requiring alignment | Many, with conflicting objectives | Few, well aligned | 3 |  |  |
| S6 | Appetite for early partial delivery | Requires complete delivery only | Values early partial capability | 4 |  |  |

## Section E — Dimension 4: Governance, Contract and Constraint Characteristics

| Ref | Criterion | Score 1–2 Indicates | Score 4–5 Indicates | Weight | Score | Weighted |
| --- | --- | --- | --- | --- | --- | --- |
| G1 | Regulatory evidence and traceability demands | Extensive fixed documentation required | Outcome-based evidence acceptable | 5 |  |  |
| G2 | Contractual delivery model | Fixed price, fixed scope | Capacity, time and materials, or outcome based | 5 |  |  |
| G3 | Funding release model | Single up-front approval against a fixed plan | Incremental funding by release | 4 |  |  |
| G4 | Safety, security or physical delivery constraints | Significant | Minimal | 4 |  |  |
| G5 | Fixed external deadline | Immovable regulatory or contractual date | Flexible | 3 |  |  |
| G6 | Audit and assurance regime | Requires fixed baselines and formal change control | Accepts iterative evidence | 4 |  |  |

## Section F — Score Summary

| Dimension | Maximum Weighted | Actual Weighted | Normalised Score (%) | Dimension Indication |
| --- | --- | --- | --- | --- |
| 1. Product and requirements | 150 |  |  |  |
| 2. Organisation and team | 125 |  |  |  |
| 3. Stakeholders and customer | 115 |  |  |  |
| 4. Governance and constraints | 125 |  |  |  |
| TOTAL | 515 |  |  |  |

NOTE Normalised score = (actual weighted ÷ maximum weighted) × 100. The maximum weighted value assumes a score of 5 against every criterion in the dimension.

## Section G — Indicated Approach

| Normalised Total Score | Indicated Approach | Typical Characteristics |
| --- | --- | --- |
| Below 40% | Predictive | Plan-driven delivery with phase gates, baselined scope, schedule and cost, and formal change control |
| 40% – 55% | Hybrid — predictive dominant | Predictive governance and baselines, with adaptive delivery inside defined work packages |
| 55% – 70% | Hybrid — adaptive dominant | Iterative delivery with predictive control over fixed-lead-time or contractually fixed components |
| Above 70% | Agile / adaptive | Iterative, incremental delivery with an empowered team, continuous stakeholder engagement and emergent scope |

| Normalised Total Score Achieved |  |
| --- | --- |
| Indicated Approach |  |
| Criteria Scoring at the Extremes (1 or 5) | ⟨ list, as these usually determine the practical approach ⟩ |
| Dimensions Materially Out of Line with the Total | ⟨ and their implication ⟩ |

## Section H — Preconditions for the Indicated Approach

| Ref | Precondition Required | Currently Satisfied | Action to Establish | Owner | Due Date | Consequence if Not Established |
| --- | --- | --- | --- | --- | --- | --- |
| PC-01 | Dedicated product owner with decision authority | No | Sponsor to confirm assignment and publish authority | Sponsor | DD-MMM | Adaptive delivery not viable; revert to predictive |

## Section I — Component-Level Approach Indication (where hybrid is indicated)

| Component / Work Stream | Dominant Characteristics | Indicated Approach | Interface With | Interface Risk |
| --- | --- | --- | --- | --- |
| Data migration | Fixed source structures, high compliance evidence demand | Predictive | Application build | Cutover timing dependency |

## Section J — Assessment Conclusion

| Conclusion | ⟨ summary statement of the indicated approach ⟩ |
| --- | --- |
| Confidence in the Assessment | ⟨ High ¦ Medium ¦ Low, with reasoning ⟩ |
| Principal Uncertainties | ⟨ factors that could change the indication ⟩ |
| Re-assessment Trigger | ⟨ what would require this assessment to be repeated ⟩ |
| Passed To | ⟨ IMT-PIG-015 Approach Selection Form, date ⟩ |

# 10.  Approval and Authorisation

By signing below, each approver confirms that the content of this document has been reviewed, is accurate to the best of their knowledge, and is authorised for use within the project.

| Approval Role | Name | Position / Title | Signature | Date |
| --- | --- | --- | --- | --- |
| Assessed by (Project Manager and Team) |  |  |  |  |
| Validated by (PMO Manager) |  |  |  |  |
| Accepted by (Project Sponsor) |  |  |  |  |

# 11.  Revision History

| Version | Date | Description of Change | Prepared / Revised By | Approved By |
| --- | --- | --- | --- | --- |
| 0.1 | DD-MMM-YYYY | Initial draft prepared for review | Project Manager | — |
| 0.9 | DD-MMM-YYYY | Reviewed by PMO; comments incorporated | PMO Analyst | — |
| 1.0 | 01-Sep-2026 | First approved and issued baseline | Project Manager | PMO Manager (methodological validation) and Project Sponsor (acceptance of the resulting approach) |

NOTE Rows shown in shaded italics are illustrative examples of how the revision history is completed. Replace them with the actual revision record.

# 12.  Notice and Disclaimer

PMI®, PMBOK®, PMP®, PMI-ACP® and PfMP® are registered marks of the Project Management Institute, Inc. This document is an original work product of IMTITHAL, developed in alignment with the principles, performance domains and focus areas described in the PMBOK® Guide – Eighth Edition. It is not issued, certified, endorsed or approved by PMI, and it does not reproduce PMI copyrighted text or proprietary PMI templates. Organisations remain responsible for tailoring this document to their own governance, contractual and regulatory obligations.