IMTITHAL PROJECT MANAGEMENT SYSTEM PMBOK® Guide – Eighth Edition Aligned

TOOLKIT 01  |  PROJECT INITIATION & GOVERNANCE

PROJECT CONSTRAINTS LOG

Identification, quantification and management of project constraints

Document Reference:  IMT-PIG-019

| DOCUMENT CONTROL |  |  |  |
| --- | --- | --- | --- |
| File Name | IMT-PIG-019_Project_Constraints_Log_v1.0.docx | Version | 1.0 |
| Document Owner | Project Management Office (PMO) | Document Status | Approved – Issued for Use |
| Approval Authority | Project Sponsor (accepts the constraint set and its consequences for the achievable outcome) | Classification | Internal – Controlled Document |
| Effective Date | 01-Sep-2026 | Revision Date | 01-Sep-2026 |
| Next Review Date | 01-Sep-2027 | Review Frequency | At every stage gate and at each monthly progress review; immediately upon any change to a constraint |

IMTITHAL Project Management System · Toolkit 01: Project Initiation & Governance This document is an original IMTITHAL work product developed in alignment with the concepts and practices of the PMBOK® Guide – Eighth Edition. PMI, PMBOK, PMP and PMI-ACP are marks of the Project Management Institute, Inc. IMTITHAL is not affiliated with, endorsed by, certified by, or approved by PMI. No PMI copyrighted text or proprietary PMI template is reproduced herein.

# 1.  Purpose

The Constraints Log records every limiting factor that restricts the options available to the project — fixed dates, budget ceilings, resource limits, technical boundaries, regulatory obligations, contractual terms and organisational policies. For each constraint it records the source, the authority that imposed it, whether it is genuinely immovable or merely inconvenient, the impact it has on the plan, and the strategy adopted to work within it or to have it relaxed. It converts a vague sense of limitation into a managed set of boundary conditions.

- Distinguishes genuine constraints from preferences that have hardened into apparent constraints.

- Identifies the authority who imposed each constraint, and therefore who can relax it.

- Quantifies the impact each constraint has on the plan and on the achievable outcome.

- Provides the factual basis for trade-off discussions with the sponsor and the governance body.

# 2.  When to Use

- During initiation, before planning options are developed.

- Before estimating and scheduling, since constraints bound the feasible solution space.

- When a plan cannot be made to work, to identify which constraint must be challenged.

- When a constraint changes, is lifted or is newly imposed.

- At each stage gate, to confirm which constraints still apply.

# 3.  Responsibility and Approval

| Governance Role | Assignment | Description of Involvement |
| --- | --- | --- |
| Responsible (prepares) | Project Manager | Prepares, populates and maintains the document; ensures accuracy and completeness of all fields. |
| Accountable (owns) | Project Manager | Single point of accountability for the quality, currency and control of the document. |
| Consulted | PMO, Finance, Risk, Quality, Legal/Contracts, business owners and technical disciplines as applicable | Provides subject-matter input before submission for approval. |
| Informed | Project team, affected business units, supporting functions, key external stakeholders | Receives the approved document through the controlled distribution list. |
| Approves | Project Sponsor (accepts the constraint set and its consequences for the achievable outcome) | Formally authorises the document; approval is recorded in the Project Approval Register. |

# 4.  Required Inputs

- Project Charter, Business Case and the approved funding envelope.

- Regulatory obligations, contractual terms and organisational policies.

- Resource availability information and organisational capacity plans.

- Technical, architectural, security and infrastructure standards.

- Portfolio-level constraints, including capacity and interdependency limits.

- Stakeholder-imposed conditions and externally fixed dates.

# 5.  Required Outputs

- A complete, classified log of constraints with sources and imposing authorities.

- Quantified impact of each constraint on scope, schedule, cost, quality and benefit.

- A management strategy per constraint, and challenge actions where relaxation is worth pursuing.

- The boundary conditions used in planning, estimating and options analysis.

# 6.  PMBOK® Guide – Eighth Edition Alignment

This document has been designed in alignment with the following elements of the PMBOK® Guide – Eighth Edition. The alignment statement is provided for conceptual traceability only.

| Focus Area | Initiating and Planning; maintained through Monitoring and Controlling |
| --- | --- |
| Performance Domains | Governance, Scope, Schedule, Finance (primary); Resources, Risk (supporting) |
| Guiding Principles | Adopt a holistic view · Focus on value · Be an accountable leader |
| Tailoring Consideration | Adaptive projects typically fix time and cost and treat scope as the flexible variable; the constraint log should record this explicitly, since it inverts the assumption underlying predictive change control. Record the constraint priority agreed in IMT-PIG-005 Section F. |

# 7.  Review Frequency and Approval Requirements

| Review Frequency | At every stage gate and at each monthly progress review; immediately upon any change to a constraint |
| --- | --- |
| Review Triggers | Change of sponsor or governance structure; change of delivery approach; stage-gate decision; material change to scope, cost, schedule, benefits or risk exposure; audit or assurance finding; organisational restructuring. |
| Approval Requirements | Accepted by the Project Sponsor. Where a constraint makes an approved objective unachievable, that fact must be escalated to the governance body for a decision rather than absorbed within the project. |
| Change Control | Any change to an approved version requires a change request assessed through the project change control process. Minor editorial changes increment the minor version; changes affecting scope, cost, schedule, benefits or governance increment the major version and require re-approval. |
| Retention | Retained for the life of the project plus the organisational records-retention period, in the Project Information and Document Register. |

# 8.  Instructions for Completion

Complete every field. Where a field is not applicable, enter "N/A" and state the reason — never leave a field blank.

- Record each constraint as a single, specific statement with a quantified limit. "Limited budget" is not a constraint; "expenditure may not exceed 2.4 million in FY27" is.

- Identify the source and the imposing authority for each constraint. A constraint whose owner cannot be identified is usually an assumption in disguise — reclassify it in the Assumptions Log.

- Classify each constraint by type and record whether it is Hard (immovable), Firm (relaxable with approval) or Soft (a preference that could be challenged).

- Quantify the impact of each constraint on scope, schedule, cost, quality and benefit. An unquantified constraint cannot be traded off.

- Record the management strategy: work within the constraint, seek relaxation, mitigate the effect, or escalate for a trade-off decision.

- Where a constraint is Firm or Soft and materially damages the achievable outcome, raise a challenge action in Section D with an owner and a decision date.

- Test the constraint set for internal conflict in Section E. Two constraints that cannot both be satisfied is a governance issue requiring immediate escalation, not a planning problem to be absorbed.

- Link each constraint to the Assumptions Log, Dependencies Register and Risk Register where a relationship exists.

- Confirm the constraint priority order with the sponsor, consistent with IMT-PIG-005 Section F, so that trade-off decisions can be made quickly under pressure.

- Review at each progress meeting and gate. Record lifted constraints explicitly — teams frequently continue to work within constraints that have long since been removed.

NOTE The live register is maintained in the IMTITHAL master Excel workbook (Constraints_Log worksheet). This document defines the controlled structure, the classification rules and the management approach.

# 9.  Template — Project Constraints Log

## Section A — Log Identification

| Project Name |  |
| --- | --- |
| Project Reference / ID |  |
| Project Manager |  |
| Log Version and Date |  |
| Total Constraints Recorded |  |
| Hard Constraints |  |
| Constraints Under Challenge |  |
| Conflicting Constraints Identified |  |
| Status | ⟨ Not Started ¦ In Progress ¦ Under Review ¦ Approved ¦ Rejected ¦ On Hold ¦ Completed ¦ Cancelled ⟩ |

## Section B — Constraint Classification

| Classification | Definition | Management Implication |
| --- | --- | --- |
| Hard | Immovable; imposed by law, regulation, physics or an executed contract | Plan within it; do not spend effort seeking relaxation |
| Firm | Relaxable, but only by a defined authority through a formal decision | Quantify the cost of the constraint; escalate a relaxation request where the benefit justifies it |
| Soft | A preference, convention or historical practice presented as a constraint | Challenge early; frequently removable at little cost |

| Constraint Type | Typical Examples | Usual Imposing Authority |
| --- | --- | --- |
| Schedule / time | Fixed regulatory deadline; seasonal window; contractual completion date | Regulator; customer; executive management |
| Financial | Budget ceiling; annual funding profile; capitalisation rules | Finance; Portfolio Board |
| Resource | Headcount cap; specialist availability; recruitment freeze | Line management; HR |
| Technical | Mandated platform, standard or architecture; capacity limits | Architecture authority; IT |
| Regulatory / legal | Licensing, data residency, privacy, accessibility obligations | Regulator; Legal |
| Contractual | Fixed scope and price; supplier obligations; liability terms | Contract; Procurement |
| Organisational / policy | Procurement thresholds; change freeze periods; approval routes | Executive management; policy owner |
| Operational | Business blackout periods; peak-season change restrictions | Operations management |
| Environmental / sustainability | Emissions limits; waste and disposal obligations | Regulator; corporate ESG policy |
| Geographic / logistical | Site access; shipping lead times; time-zone overlap | External conditions |

## Section C — Constraints Log

| Ref | Date Raised | Constraint Statement (quantified) | Type | Class | Source / Imposing Authority | Impact on the Plan | Management Strategy | Owner | Review Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CN-01 | DD-MMM | No production change permitted between 15-Dec and 05-Jan | Operational | Hard | Operations Director — peak trading policy | Go-live cannot occur in that window; deployment moves to Jan | Plan deployment for 08-Jan; use the freeze for readiness activity | PM | DD-MMM | Active |

## Section D — Constraint Challenge Actions

| Ref | Constraint Ref | Case for Relaxation | Value of Relaxation | Relaxation Authority | Action Owner | Decision Due | Outcome |
| --- | --- | --- | --- | --- | --- | --- | --- |
| CC-01 | CN-03 | Mandated platform adds 6 months and 400k for no functional gain | Saves 6 months and 400k | Architecture Board | Solution Architect | DD-MMM | Pending |

## Section E — Constraint Conflict Analysis

| Ref | Constraints in Conflict | Nature of the Conflict | Consequence if Unresolved | Resolution Options | Escalated To | Resolution |
| --- | --- | --- | --- | --- | --- | --- |
| CF-01 | CN-01 and CN-05 | Regulatory deadline of 31-Dec falls inside the change freeze | Either the regulatory obligation or the operational policy is breached | Seek a freeze exemption; seek a regulatory extension; deliver early | Steering Committee | Pending |

## Section F — Constraint Change Record

| Date | Constraint Ref | Change (imposed / relaxed / lifted / re-classified) | Authority | Impact on the Plan | Action Taken |
| --- | --- | --- | --- | --- | --- |

# 10.  Approval and Authorisation

By signing below, each approver confirms that the content of this document has been reviewed, is accurate to the best of their knowledge, and is authorised for use within the project.

| Approval Role | Name | Position / Title | Signature | Date |
| --- | --- | --- | --- | --- |
| Maintained by (Project Manager) |  |  |  |  |
| Reviewed by (PMO) |  |  |  |  |
| Accepted by (Project Sponsor) |  |  |  |  |

# 11.  Revision History

| Version | Date | Description of Change | Prepared / Revised By | Approved By |
| --- | --- | --- | --- | --- |
| 0.1 | DD-MMM-YYYY | Initial draft prepared for review | Project Manager | — |
| 0.9 | DD-MMM-YYYY | Reviewed by PMO; comments incorporated | PMO Analyst | — |
| 1.0 | 01-Sep-2026 | First approved and issued baseline | Project Manager | Project Sponsor (accepts the constraint set and its consequences for the achievable outcome) |

NOTE Rows shown in shaded italics are illustrative examples of how the revision history is completed. Replace them with the actual revision record.

# 12.  Notice and Disclaimer

PMI®, PMBOK®, PMP®, PMI-ACP® and PfMP® are registered marks of the Project Management Institute, Inc. This document is an original work product of IMTITHAL, developed in alignment with the principles, performance domains and focus areas described in the PMBOK® Guide – Eighth Edition. It is not issued, certified, endorsed or approved by PMI, and it does not reproduce PMI copyrighted text or proprietary PMI templates. Organisations remain responsible for tailoring this document to their own governance, contractual and regulatory obligations.