IMTITHAL PROJECT MANAGEMENT SYSTEM PMBOK® Guide – Eighth Edition Aligned

TOOLKIT 01  |  PROJECT INITIATION & GOVERNANCE

PROJECT KICK-OFF MEETING AGENDA

Structured agenda for the project mobilisation meeting

Document Reference:  IMT-PIG-023

| DOCUMENT CONTROL |  |  |  |
| --- | --- | --- | --- |
| File Name | IMT-PIG-023_Project_Kick_Off_Meeting_Agenda_v1.0.docx | Version | 1.0 |
| Document Owner | Project Management Office (PMO) | Document Status | Approved – Issued for Use |
| Approval Authority | Project Sponsor (approves the agenda and opens the meeting) | Classification | Internal – Controlled Document |
| Effective Date | 01-Sep-2026 | Revision Date | 01-Sep-2026 |
| Next Review Date | 01-Sep-2027 | Review Frequency | Per project (used once per kick-off); the template is reviewed annually |

IMTITHAL Project Management System · Toolkit 01: Project Initiation & Governance This document is an original IMTITHAL work product developed in alignment with the concepts and practices of the PMBOK® Guide – Eighth Edition. PMI, PMBOK, PMP and PMI-ACP are marks of the Project Management Institute, Inc. IMTITHAL is not affiliated with, endorsed by, certified by, or approved by PMI. No PMI copyrighted text or proprietary PMI template is reproduced herein.

# 1.  Purpose

The Kick-Off Meeting Agenda structures the meeting at which the project is formally mobilised: the authorisation is communicated, the objectives and success criteria are shared, the scope boundaries and delivery approach are explained, roles and governance are made explicit, ways of working are agreed, and the initial risks, assumptions and dependencies are surfaced with the whole team present. A properly structured kick-off establishes shared understanding and commitment at the point where they are cheapest to create.

- Ensures the whole team leaves with the same understanding of purpose, scope and approach.

- Makes governance, roles, authority and escalation explicit from day one.

- Establishes agreed ways of working, cadence and communication protocols.

- Surfaces risks, assumptions, constraints and dependencies while the plan is still adjustable.

# 2.  When to Use

- Immediately after the Project Charter is approved and before delivery work begins.

- At the start of a major new phase, where team composition changes substantially.

- When a significant new supplier or partner team joins the project.

- When a project restarts after suspension, or after a change of project manager.

# 3.  Responsibility and Approval

| Governance Role | Assignment | Description of Involvement |
| --- | --- | --- |
| Responsible (prepares) | Project Manager (prepares and facilitates) | Prepares, populates and maintains the document; ensures accuracy and completeness of all fields. |
| Accountable (owns) | Project Manager | Single point of accountability for the quality, currency and control of the document. |
| Consulted | PMO, Finance, Risk, Quality, Legal/Contracts, business owners and technical disciplines as applicable | Provides subject-matter input before submission for approval. |
| Informed | Project team, affected business units, supporting functions, key external stakeholders | Receives the approved document through the controlled distribution list. |
| Approves | Project Sponsor (approves the agenda and opens the meeting) | Formally authorises the document; approval is recorded in the Project Approval Register. |

# 4.  Required Inputs

- Approved Project Charter and Business Case summary.

- Objectives and Success Criteria Form (IMT-PIG-005).

- Governance Structure (IMT-PIG-009), RACI Matrix (IMT-PIG-013) and Organisation Chart (IMT-PIG-014).

- Approach Selection Form (IMT-PIG-015) and the outline plan or roadmap.

- Initial Risk Register, Assumptions Log, Constraints Log and Dependencies Register.

- Confirmed attendee list and their roles.

# 5.  Required Outputs

- A circulated agenda with pre-reading, timings and named presenters.

- A shared understanding of purpose, scope, approach, governance and ways of working.

- Agreed team norms, cadence and communication protocols.

- Newly identified risks, assumptions, constraints and dependencies.

- A defined action list captured in the Kick-Off Meeting Minutes (IMT-PIG-024).

# 6.  PMBOK® Guide – Eighth Edition Alignment

This document has been designed in alignment with the following elements of the PMBOK® Guide – Eighth Edition. The alignment statement is provided for conceptual traceability only.

| Focus Area | Initiating (transition into Planning and Executing) |
| --- | --- |
| Performance Domains | Stakeholders and Resources (primary); Governance, Scope, Risk (supporting) |
| Guiding Principles | Build an empowered culture · Be an accountable leader · Focus on value · Adopt a holistic view |
| Tailoring Consideration | Adaptive projects extend the agenda to include the product vision, the initial backlog walkthrough, the definition of done, and the first iteration planning. Small projects may compress the agenda to ninety minutes while retaining every agenda heading. |

# 7.  Review Frequency and Approval Requirements

| Review Frequency | Per project (used once per kick-off); the template is reviewed annually |
| --- | --- |
| Review Triggers | Change of sponsor or governance structure; change of delivery approach; stage-gate decision; material change to scope, cost, schedule, benefits or risk exposure; audit or assurance finding; organisational restructuring. |
| Approval Requirements | The agenda is approved by the Project Sponsor before circulation. The Charter must be approved before the kick-off is held. |
| Change Control | Any change to an approved version requires a change request assessed through the project change control process. Minor editorial changes increment the minor version; changes affecting scope, cost, schedule, benefits or governance increment the major version and require re-approval. |
| Retention | Retained for the life of the project plus the organisational records-retention period, in the Project Information and Document Register. |

# 8.  Instructions for Completion

Complete every field. Where a field is not applicable, enter "N/A" and state the reason — never leave a field blank.

- Hold the kick-off only after the Charter is approved. A kick-off held before authorisation creates commitment to something not yet sanctioned.

- Circulate the agenda together with the pre-reading pack at least five working days in advance. Attendees who have not read the Charter cannot contribute meaningfully.

- Assign a named presenter and a time allocation to every agenda item. Unallocated items are the reason kick-off meetings overrun and end without the risk discussion.

- Have the sponsor — not the project manager — open the meeting and state why the project matters. Visible sponsorship at kick-off materially affects engagement.

- Allocate genuine time to the interactive items in Sections D and E. A kick-off consisting entirely of presentation wastes the one occasion when the whole team is together.

- Cover governance, roles, authority and escalation explicitly. Most escalation failures during delivery trace back to a kick-off that skipped this section.

- Agree ways of working in the meeting rather than presenting them: cadence, tools, response expectations, decision protocol and meeting norms.

- Run the risk, assumption and dependency session as a facilitated exercise. Capture everything raised; assign owners in the meeting.

- Close with the actions, owners and dates, and confirm the immediate next steps and the date of the first progress review.

- Issue the minutes (IMT-PIG-024) within two working days while the discussion is still fresh.

# 9.  Template — Project Kick-Off Meeting Agenda

## Section A — Meeting Details

| Project Name |  |
| --- | --- |
| Project Reference / ID |  |
| Meeting Title | ⟨ Project Kick-Off Meeting ⟩ |
| Date and Time |  |
| Duration | ⟨ e.g. 3 hours ⟩ |
| Location / Channel |  |
| Chair | ⟨ Project Sponsor ⟩ |
| Facilitator | ⟨ Project Manager ⟩ |
| Minute Taker |  |
| Meeting Objective | ⟨ mobilise the project team with a shared understanding of purpose, scope, approach and governance ⟩ |
| Pre-Reading Circulated On |  |
| Status | ⟨ Not Started ¦ In Progress ¦ Under Review ¦ Approved ¦ Rejected ¦ On Hold ¦ Completed ¦ Cancelled ⟩ |

## Section B — Attendees

| Name | Role in the Project | Organisation | Required / Optional | Presenting | Confirmed |
| --- | --- | --- | --- | --- | --- |

## Section C — Pre-Reading Pack

| Ref | Document | Version | Purpose of Reading | Location |
| --- | --- | --- | --- | --- |
| PR-01 | Project Charter | v1.0 | Understand the authorisation, objectives and boundaries | Project workspace / DR-014 |

## Section D — Agenda

| # | Time | Agenda Item | Content and Purpose | Presenter | Format |
| --- | --- | --- | --- | --- | --- |
| 1 | 10 min | Welcome, sponsor address and meeting objectives | Why this project matters to the organisation; executive commitment; what the meeting must achieve | Project Sponsor | Presentation |
| 2 | 10 min | Introductions | Each attendee: name, role in the project, what they bring, what they need from others | All | Round table |
| 3 | 15 min | Business context and business case summary | The problem, the opportunity, the expected benefits and the benefit owners | Business Owner | Presentation |
| 4 | 15 min | Project charter walkthrough | Authorisation, objectives, success criteria, scope boundaries, funding envelope, PM authority | Project Manager | Presentation and Q&A |
| 5 | 15 min | Objectives and success criteria | How success will be measured, by whom and when; acceptance basis | Project Manager | Discussion |
| 6 | 15 min | Scope: in, out and known grey areas | Explicit inclusions and exclusions; where boundaries are still to be settled | Project Manager | Discussion |
| 7 | 15 min | Delivery approach and life cycle | Approach selected and why; phases or iterations; cadence; definition of done | Project Manager | Presentation |
| 8 | 15 min | Governance, roles and authority | Governance bodies; decision rights; authority thresholds; escalation path and response times | PMO / Project Manager | Presentation |
| 9 | 15 min | Team structure and responsibilities | Organisation chart; RACI walkthrough; interfaces; time commitments | Project Manager | Discussion |
| 10 | 10 min | Outline plan, milestones and immediate priorities | Roadmap, key milestones, gate dates and the first 30 days | Project Manager | Presentation |
| 11 | 25 min | Risks, assumptions, constraints and dependencies | Facilitated identification; capture and assign owners in the meeting | Project Manager | Facilitated workshop |
| 12 | 20 min | Ways of working and team norms | Cadence, tools, communication protocols, response expectations, decision protocol, conflict resolution | All | Facilitated agreement |
| 13 | 10 min | Reporting, communication and information management | Reports, frequency, recipients; where documents live; version control | PMO | Presentation |
| 14 | 10 min | Quality, compliance, safety and sustainability obligations | Standards applied, mandatory controls, obligations everyone must observe | Quality / Compliance | Presentation |
| 15 | 15 min | Open discussion, concerns and expectations | Space for the team to raise concerns and set expectations of each other | All | Open discussion |
| 16 | 10 min | Actions, next steps and close | Confirm actions and owners; next milestones; date of the first progress review | Project Manager | Summary |

NOTE Timings above total approximately three hours and twenty-five minutes including transitions. For a compressed ninety-minute kick-off, retain every agenda heading and reduce items 3, 6, 9, 13 and 14 to a briefing note in the pre-reading pack.

## Section E — Facilitated Session Preparation

| Session | Prompt Questions to Use | Capture Method | Output Register | Facilitator |
| --- | --- | --- | --- | --- |
| Risk identification | What could stop us? What has gone wrong on similar work? What are we assuming? | Cards then grouping | Risk Register / Assumptions Log | Project Manager |

## Section F — Ways of Working to Be Agreed

| Topic | Question to Settle | Agreement Reached |
| --- | --- | --- |
| Meeting cadence | Which recurring meetings, how often, how long, who attends? |  |
| Progress reporting | What is reported, by whom, by when, in what format? |  |
| Communication channels | Which channel for which purpose; expected response times? |  |
| Decision protocol | How are decisions made and recorded when the group cannot agree? |  |
| Escalation | When does an issue escalate, to whom, and how quickly? |  |
| Document management | Where do documents live; naming and version control? |  |
| Working hours and availability | Core hours, time zones, on-call and leave arrangements? |  |
| Quality and review | What is peer reviewed, by whom, before it is considered done? |  |
| Conflict resolution | How are disagreements handled and by whom? |  |
| Recognition and team health | How is good work recognised and team health monitored? |  |

## Section G — Logistics Checklist

| Item | Owner | Due Before Meeting | Status |
| --- | --- | --- | --- |
| Room, video link and recording arrangements confirmed | Project Coordinator | 3 working days | Complete |

# 10.  Approval and Authorisation

By signing below, each approver confirms that the content of this document has been reviewed, is accurate to the best of their knowledge, and is authorised for use within the project.

| Approval Role | Name | Position / Title | Signature | Date |
| --- | --- | --- | --- | --- |
| Prepared by (Project Manager) |  |  |  |  |
| Approved by (Project Sponsor) |  |  |  |  |

# 11.  Revision History

| Version | Date | Description of Change | Prepared / Revised By | Approved By |
| --- | --- | --- | --- | --- |
| 0.1 | DD-MMM-YYYY | Initial draft prepared for review | Project Manager | — |
| 0.9 | DD-MMM-YYYY | Reviewed by PMO; comments incorporated | PMO Analyst | — |
| 1.0 | 01-Sep-2026 | First approved and issued baseline | Project Manager | Project Sponsor (approves the agenda and opens the meeting) |

NOTE Rows shown in shaded italics are illustrative examples of how the revision history is completed. Replace them with the actual revision record.

# 12.  Notice and Disclaimer

PMI®, PMBOK®, PMP®, PMI-ACP® and PfMP® are registered marks of the Project Management Institute, Inc. This document is an original work product of IMTITHAL, developed in alignment with the principles, performance domains and focus areas described in the PMBOK® Guide – Eighth Edition. It is not issued, certified, endorsed or approved by PMI, and it does not reproduce PMI copyrighted text or proprietary PMI templates. Organisations remain responsible for tailoring this document to their own governance, contractual and regulatory obligations.